# ArogyaSetu

## Mobile Healthcare & Preventive Health Initiative

### For Mining-Affected Rural & Tribal Communities

### Jayashankar Bhupalpally District, Telangana

### Under District Mineral Foundation Trust (DMFT) / PMKKKY

Presented as: # MP Initiative under DMFT

Implementation Support: Give For Society

# SECTION 11 — DETAILED BUDGET FRAMEWORK

## Semi-DPR Financial Structure

The proposed ArogyaSetu initiative is designed as a district-level preventive healthcare outreach and mobile medical infrastructure programme under the District Mineral Foundation Trust (DMFT) / PMKKKY framework.

The budget framework has been prepared based on:

- mobile healthcare outreach,

- preventive health screening,

- PHC-linked medical camp circuits,

- telemedicine support systems,

- diagnostic screening infrastructure,

- and rural healthcare accessibility strengthening.

The proposed financial structure emphasizes: # Sustainable Preventive Healthcare Outreach Systems through convergence-driven district health delivery models.

# FROZEN PHASE-1 IMPLEMENTATION MODEL

| Parameter | Approved Assumption |
| --- | --- |
| Deployment Model | 1 Mobile Medical Screening Van + 6 PHC Camp Circuits |
| Geographic Coverage | Mining-Affected & Tribal Mandals |
| Operational Model | Hybrid PHC Convergence Model |
| Doctor Deployment | 1 Dedicated Doctor |
| Nurse Deployment | 1 Dedicated Nurse |
| Technician Model | Rotational PHC Support |
| Camp Frequency | Monthly |
| Telemedicine Model | Moderate |
| Implementation Duration | 2 Years |
| Programme Type | Preventive Healthcare Outreach |

# SECTION A — ADVANCED MOBILE MEDICAL SCREENING VAN (CAPEX)

## Scope

Procurement and customization of: # Advanced Mobile Medical Screening Van

with integrated diagnostic and telemedicine support systems.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Medical Van Chassis | 1 | ₹22,00,000 | ₹22,00,000 |
| Medical Vehicle Customization | 1 | ₹14,00,000 | ₹14,00,000 |
| Electrical & Power Backup Systems | 1 | ₹4,00,000 | ₹4,00,000 |
| Internal Medical Furniture & Fixtures | 1 | ₹3,50,000 | ₹3,50,000 |
| Branding & IEC Exterior Design | 1 | ₹1,50,000 | ₹1,50,000 |
| GPS & Tracking Systems | 1 | ₹1,00,000 | ₹1,00,000 |
| Telemedicine Connectivity Setup | 1 | ₹2,50,000 | ₹2,50,000 |

### Subtotal

# ₹48,50,000

# SECTION B — MEDICAL DIAGNOSTIC EQUIPMENT

## Scope

Medical diagnostic equipment for:

- preventive screening,

- basic diagnostics,

- telemedicine-assisted consultation,

- and rural outreach healthcare services.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| ECG Machine | 1 | ₹1,50,000 | ₹1,50,000 |
| BP Monitoring Systems | 4 | ₹15,000 | ₹60,000 |
| Glucometer Systems | 4 | ₹10,000 | ₹40,000 |
| Hemoglobin Testing Kits | 2 | ₹40,000 | ₹80,000 |
| Vision Screening Equipment | 1 | ₹1,00,000 | ₹1,00,000 |
| Dental Screening Kits | 2 | ₹50,000 | ₹1,00,000 |
| Portable Examination Equipment | Lump Sum | — | ₹2,00,000 |
| Tablets/Laptops for Health Records | 4 | ₹50,000 | ₹2,00,000 |
| Medical Consumables (Initial Setup) | Lump Sum | — | ₹3,00,000 |

### Subtotal

# ₹12,30,000

# SECTION C — STAFFING & HUMAN RESOURCES

## Scope

Hybrid convergence staffing model integrating:

- dedicated medical personnel,

- district coordination,

- and PHC-linked technical support.

## Budget Components (2 Years)

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Doctor Honorarium | 24 Months | ₹80,000/month | ₹19,20,000 |
| Nurse Honorarium | 24 Months | ₹45,000/month | ₹10,80,000 |
| Driver Salary | 24 Months | ₹25,000/month | ₹6,00,000 |
| District Programme Coordinator | 24 Months | ₹50,000/month | ₹12,00,000 |
| PHC Technician Support | Lump Sum | — | ₹6,00,000 |
| Administrative Support | Lump Sum | — | ₹4,00,000 |

### Subtotal

# ₹58,00,000

# SECTION D — PHC-BASED MONTHLY HEALTH CAMP CIRCUITS

## Scope

Implementation of: # 6 Monthly PHC-Linked Outreach Circuits

covering:

- mining-affected villages,

- tribal habitations,

- schools,

- hostels,

- and underserved communities.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Monthly Health Camps | 144 Camps | ₹20,000 | ₹28,80,000 |
| Outreach IEC Materials | Lump Sum | — | ₹5,00,000 |
| Community Awareness Campaigns | Lump Sum | — | ₹4,00,000 |
| Camp Logistics & Mobility | Lump Sum | — | ₹8,00,000 |
| Referral Coordination Support | Lump Sum | — | ₹3,00,000 |

### Subtotal

# ₹48,80,000

# SECTION E — TELEMEDICINE & DIGITAL HEALTH SYSTEMS

## Scope

Telemedicine-enabled rural healthcare connectivity systems supporting:

- remote consultation,

- specialist referrals,

- digital health records,

- and tele-health accessibility.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Telemedicine Software Systems | Lump Sum | — | ₹4,00,000 |
| Internet & Connectivity Support | 24 Months | ₹15,000/month | ₹3,60,000 |
| Cloud-Based Health Records | Lump Sum | — | ₹2,50,000 |
| Digital Reporting & MIS Systems | Lump Sum | — | ₹3,00,000 |

### Subtotal

# ₹13,10,000

# SECTION F — VEHICLE OPERATIONS & MAINTENANCE

## Scope

Operational support for:

- vehicle mobility,

- fuel,

- servicing,

- maintenance,

- and field deployment systems.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Fuel & Field Mobility | 24 Months | ₹60,000/month | ₹14,40,000 |
| Vehicle Insurance | 2 Years | ₹1,00,000/year | ₹2,00,000 |
| Vehicle Maintenance | Lump Sum | — | ₹5,00,000 |
| Equipment Servicing | Lump Sum | — | ₹3,00,000 |

### Subtotal

# ₹24,40,000

# SECTION G — MONITORING, REPORTING & DISTRICT COORDINATION

## Scope

Programme monitoring, district coordination, reporting, beneficiary tracking, and implementation review systems.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Monitoring & Evaluation | Lump Sum | — | ₹6,00,000 |
| Reporting & Documentation | Lump Sum | — | ₹4,00,000 |
| District Review Meetings | Lump Sum | — | ₹3,00,000 |
| Data Collection & Analytics | Lump Sum | — | ₹4,00,000 |

### Subtotal

# ₹17,00,000

# SECTION H — CONTINGENCY & EMERGENCY RESERVE

| Component | Total |
| --- | --- |
| Contingency Reserve | ₹10,00,000 |

# PHASE-1 CONSOLIDATED BUDGET SUMMARY

| Component | Total |
| --- | --- |
| Mobile Medical Van CAPEX | ₹48,50,000 |
| Medical Diagnostic Equipment | ₹12,30,000 |
| Staffing & Human Resources | ₹58,00,000 |
| PHC Health Camp Circuits | ₹48,80,000 |
| Telemedicine Systems | ₹13,10,000 |
| Vehicle Operations & Maintenance | ₹24,40,000 |
| Monitoring & Coordination | ₹17,00,000 |
| Contingency Reserve | ₹10,00,000 |

# TOTAL ESTIMATED PHASE-1 BUDGET

# ₹2,32,10,000

## (₹2.32 Crores)

# COST POSITIONING UNDER DMFT

The proposed financial structure has been designed as: # Preventive Healthcare Outreach Infrastructure with:

- district-level convergence,

- mobile diagnostics,

- telemedicine systems,

- and institutional healthcare accessibility.

This approach strengthens:

- sustainability,

- operational feasibility,

- and district healthcare integration.

# COST EFFICIENCY INDICATORS

| Indicator | Estimate |
| --- | --- |
| Cost per Mandal Circuit | ~₹38 Lakhs |
| Direct Beneficiaries | 50,000+ |
| Cost per Beneficiary | ~₹450 |
| Monthly Outreach Circuits | 6 |
| Camp Coverage | 144 Camps |

# IMPLEMENTATION PHASE STRUCTURE

| Phase | Timeline |
| --- | --- |
| Phase 1 | Baseline assessment & district coordination |
| Phase 2 | Vehicle procurement & customization |
| Phase 3 | Equipment installation & staffing |
| Phase 4 | PHC outreach activation |
| Phase 5 | Telemedicine & health camp rollout |
| Phase 6 | Monitoring & district review |

# PROPOSED EXPANSION MODEL

Following successful Phase-1 implementation:

- additional outreach circuits,

- specialized women health camps,

- school health systems,

- and expanded tribal outreach

may be considered under future DMFT phases.

# FINANCIAL SUSTAINABILITY APPROACH

The initiative emphasizes:

- PHC convergence,

- preventive healthcare systems,

- mobile outreach efficiency,

- and district-level institutional integration.

This strengthens: # long-term sustainability and scalable rural healthcare accessibility across mining-affected communities.