# Sthree Swabhiman – Menstrual Hygiene and Dignity Initiative for Girls in MJPTBCWREIS Residential Schools and Junior Colleges, Telangana

### Executive Summary

Menstrual hygiene is a pressing public health concern, particularly for adolescent girls in socially and educationally disadvantaged communities. In Telangana, girls studying in government residential educational institutions under the Mahatma Jyotiba Phule Telangana Backward Classes Welfare Residential Educational Institutions Society (MJPTBCWREIS) face barriers related to menstrual stigma, lack of awareness, and limited access to sanitary products.

The Sthree Swabhiman initiative proposes a structured and scalable model to promote menstrual hygiene management (MHM) across all MJPTBCWREIS 146 girls-only residential schools and 129 girls-only junior colleges, reaching approximately 1,23,000 adolescent girls across Telangana. The initiative integrates health education, product access, and school-led delivery to foster long-term behavioral change and dignity-centered hygiene practices.

### Key Features of the Program:

- Annual menstrual health awareness sessions in every MJPTBCWREIS girls’ school and junior college.

- One-time sanitary napkin starter kits (12 packs) distributed to newly enrolled girls in Classes VI to XII and junior college (Intermediate I year).

- Training of school and college staff and peer mentors to deliver sessions sustainably in future years.

- Use of Telugu IEC materials (flipbooks, story-based visuals, posters) to normalize menstruation and improve comfort.

- Light-touch monitoring and year-end reporting to track outcomes and feedback.

### Why It Matters:

Studies and field reports show that:

- Girls in rural Telangana miss 4–5 days of school or college each month due to menstruation.

- Many still use unsafe materials like cloth, paper, or ash due to high pad costs or lack of availability.

- Period stigma persists due to cultural taboos and silence at school, college, and home.

### Alignment with UN Sustainable Development Goals:

| SDG | Contribution |
| --- | --- |
| SDG 3 – Good Health and Well-being | Improves menstrual hygiene and reduces infections. |
| SDG 4 – Quality Education | Reduces absenteeism and dropout due to menstruation. |
| SDG 5 – Gender Equality | Empowers girls through knowledge and dignity. |
| SDG 6 – Clean Water and Sanitation | Promotes safe disposal and hygiene practices. |
| SDG 10 – Reduced Inequalities | Supports marginalized BC, SC, ST, and minority girls. |
| SDG 17 – Partnerships for the Goals | Leverages CSR and NGO collaboration. |

This initiative goes beyond product delivery — it’s about creating a confident, health-literate generation of young women in Telangana’s backward classes welfare institutions.

### 2. Problem Statement

Menstruation is a natural biological process, yet in many parts of rural and tribal Telangana, it continues to be surrounded by silence, stigma, and harmful myths. This lack of awareness — combined with limited access to affordable hygiene products — leads to significant health, educational, and social consequences for adolescent girls, particularly those enrolled in government-run residential institutions under MJPTBCWREIS.

Girls studying in MJPTBCWREIS residential schools and junior colleges — largely from BC, SC, ST, and minority backgrounds — face systemic and cultural barriers that impact their health, dignity, and education during menstruation.

### Key Issues Identified:

Lack of Menstrual Awareness:
 	A large number of adolescent girls begin menstruating with little or no knowledge about the process. Cultural taboos and a lack of structured menstrual health education in schools and colleges prevent open discussion, reinforcing fear, confusion, and shame.

Poor Hygiene Practices:
	 According to NFHS-5 data and field studies in Telangana, over 50% of rural women and girls still use unhygienic alternatives like cloth, sand, ash, or newspaper — often reused without proper cleaning. This increases the risk of reproductive tract infections (RTIs), urinary tract infections (UTIs), and skin-related issues.

Inaccessibility and High Costs:
 	Commercial sanitary napkins remain either unavailable or unaffordable (₹25–₹40 per pack) for many families. Even in institutional setups, regular and adequate access is not guaranteed, and government schemes are inconsistent in their coverage.

School and College Absenteeism:
 	Girls in residential schools and junior colleges often miss 4–5 days each month during menstruation due to lack of sanitary pads, clean private toilets, or fear of leaks and social embarrassment. Such absenteeism adversely affects academic performance and, in some cases, contributes to dropout.

Lack of Disposal Infrastructure:
 	Even when sanitary napkins are available, the absence of safe, private, and eco-friendly disposal mechanisms in many campuses leads to environmental pollution, shame, and unhygienic practices like burning in open spaces.

Missed Economic and Leadership Opportunities for Girls and Women:
 	Menstrual stigma curtails girls’ participation in leadership and extracurricular activities. Simultaneously, rural and urban poor women lack livelihood avenues — although local production of sanitary napkins offers potential to bridge menstrual access gaps while generating income.

3. Project Objectives

The Sthree Swabhiman initiative seeks to empower adolescent girls studying in MJPTBCWREIS residential schools and junior colleges across Telangana with knowledge, confidence, and initial support to manage menstruation with dignity and hygiene. Rather than creating dependency on long-term product subsidies, the program aims to instill menstrual health as a personal responsibility and life skill.

### Core Objectives of the Project:

- To deliver structured menstrual hygiene awareness sessions once per academic year in each girls-only residential school and junior college under MJPTBCWREIS.

- To equip all newly enrolled adolescent girls (Classes 6–12 and Junior College First Year) with a one-time starter sanitary napkin kit, enabling them to adopt safe and hygienic menstrual practices.

- To promote menstruation as a health and hygiene priority, not a taboo, by embedding it into institutional culture through open discussions, peer mentoring, and visual awareness tools.

- To train wardens, teachers, and peer student leaders within each institution to independently conduct the program in future years using reusable educational content and formats.

- To create a scalable and replicable delivery model that reaches all 146 residential schools and 129 junior colleges for girls, serving over 1,23,000 students annually with minimal recurring overhead for the NGO.

- To normalize the conversation around menstruation as part of adolescent well-being, thereby increasing school and college participation, reducing discomfort and shame, and fostering healthier lifelong practices.

- Target Beneficiaries

This initiative targets adolescent girls enrolled in the 146 girls-only MJPTBCWREIS Residential Schools (Classes VI to XII) and 129 MJPTBCWREIS Junior Colleges for Girls (Intermediate I and II year), which serve primarily BC, SC, ST, and minority students from underserved and economically backward communities across Telangana.

### Institutional Snapshot:

- 146 Girls-Only Residential Schools across Telangana

- 129 Girls-Only Junior Colleges under MJPTBCWREIS

- Estimated total enrollment: ~1,23,000 girls and ~62500 adolescent girls.

- All institutions are fully residential with free education, meals, and basic facilities

### Primary Beneficiaries:

- Adolescent girls (Classes VI–XII and Intermediate I & II Year) across 275 institutions

- Estimated reach: ~1,23,000 girls

### Secondary Beneficiaries:

- Lady wardens, science/biology teachers, and peer hygiene leaders trained to facilitate awareness sessions

- School and junior college management staff responsible for program sustainability

### 5. Project Components

The Sthree Swabhiman initiative follows a practical, high-impact model centered around a once-a-year intervention in each government residential school for girls. Rather than implementing ongoing monthly product distribution, the project emphasizes awareness, dignity, and self-reliance — supported by an annual sanitary pad kit to promote healthy adoption of hygienic practices.

The program is structured around three integrated components that work together to ensure long-term behavioral change and institutional sustainability.

### A. Menstrual Hygiene Awareness and Education

Objective: To ensure that every newly enrolled adolescent girl receives foundational, stigma-free education about menstruation, hygiene, and emotional well-being.

Key Activities:

- Conduct one interactive awareness session per school annually, aligned with the academic calendar (typically in June–July).

- Deliver sessions through a mix of:

  - Trained school staff (wardens, science/biology teachers)

  - Local health educators (NGO/district PHC support)

  - Senior student peer leaders

- Content Themes:

  - Understanding the menstrual cycle and physical changes

  - Breaking myths and taboos around menstruation

  - Best hygiene practices and disposal methods

  - Nutrition, mental health, and body confidence

- Delivery Tools:

  - Visual aids and Telugu-language IEC handouts

  - Demonstration materials and story-based Q&A

  - Small-group discussions and confidence-building games

### B. One-Time Sanitary Napkin Kit Distribution (Annual)

Objective: To provide all newly enrolled girls with an annual sanitary pad supply to kick-start hygienic habits — without encouraging long-term subsidy expectations.

Key Activities:

- Each girl receives a kit during the awareness session, containing:

- 12 packs of sanitary napkins (covering ~1 full academic year)

- A pictorial leaflet/user guide on safe usage and disposal

- Napkin procurement is done via affordable, Make-in-India vendors at ~₹45 per pack

- Framed as a one-time dignity starter, not a continuous free supply

- Encourages girls to value menstrual hygiene as part of their routine self-care — similar to soap, undergarments, or personal items

C. School Capacity Building and Sustainability Model

Objective: To enable each institution to independently deliver menstrual health education every year — even without continued NGO presence.

Key Activities:

- Train 2–3 focal persons per school through a Training of Trainers (ToT) program:

  - Lady warden

  - Science/biology teacher

  - Senior peer mentor/student

- Provide schools with a reusable IEC toolkit, including:

  - Laminated posters

  - Flipbooks or presentation slides

  - Session scripts in Telugu

- Appoint Peer Hygiene Leaders in each batch to guide incoming students in future years

- NGO continues to play a light-touch support role in Year 2 and Year 3, enabling the school to take full ownership by Year 4

## 6. Implementation Model

The Sthree Swabhiman project follows a simple, scalable implementation cycle aligned with the academic calendar of Telangana’s government residential schools under KGBVs. It ensures that every newly enrolled adolescent girl receives menstrual health awareness and starter support once per academic year — without placing recurring operational burden on the NGO or the school system.

The model emphasizes behavior change, school-led continuity, and starter support, not long-term product dependency.

### Phase 1: Planning and School Coordination (April – May)

- Finalize the list of participating KGBVs girls-only schools for the academic year.

- Coordinate with KGBVs zonal officers, principals, and wardens to align dates and logistical plans.

- Confirm student intake estimates and starter kit quantities per school.

### Phase 2: Capacity Building and Material Preparation (May – June)

- Conduct Training of Trainers (ToT) workshops for 2–3 designated staff per school (e.g., lady warden, science teacher).

- Train selected senior girl students as Peer Hygiene Mentors to support facilitation.

- Prepare and distribute reusable IEC content, including posters, charts, session guides, and product instructions.

### Phase 3: Awareness Event and Starter Kit Distribution (June – July)

- Organize a one-day awareness event in each school shortly after reopening.

- Conduct sessions using interactive, student-friendly methods covering:

  - Menstrual cycle, hygiene practices, emotional well-being, and myth-busting

- Distribute starter kits to each girl (e.g., sanitary pad packs + leaflet).

- Encourage peer discussion, open Q&A, and message reinforcement through follow-up classroom discussions.

### Phase 4: School-Led Continuity (August – March)

- Trained staff and peer mentors will independently repeat key messages during:

  - Adolescent health clubs

  - Science periods or personal health sessions

- Schools will maintain and display awareness materials in common areas.

- Girls are encouraged to continue safe practices through personal responsibility and local purchase.

### Phase 5: Monitoring, Feedback, and Light Touch Support (Quarterly)

- NGO team conducts light-touch monitoring through:

  - Monthly call check-ins with wardens

  - Sample feedback forms from girls

  - Field visits to a few sample schools per district

- Collect success stories, improvement suggestions, and data on perceived impact.

- NGO prepares a year-end report and refreshes training materials for the next cycle.

This model ensures that the initiative is:

- Efficient: Only one-day delivery per school each year

- Effective: Every new girl is equipped early in the school year

- Sustainable: Ongoing awareness maintained by school staff, not NGO field teams

- Scalable: Easily replicable across 173+ institutions statewide

## 7. Implementation Timeline

The Sthree Swabhiman initiative follows an annual academic cycle, with all key activities clustered around school reopening and onboarding of new students. This schedule ensures that every newly enrolled adolescent girl receives menstrual health education and starter support early in the year, with sustainability mechanisms embedded through school-based training and peer-led reinforcement.

This timeline is based on a standard academic year of 9 months (typically June to March).

| Phase | Timeline | Key Activities |
| --- | --- | --- |
| Phase 1: Planning & School Finalization | April – May | - Identify participating schools for the academic year - Estimate student intake and kit quantities - Coordinate with school heads and zonal officers |
| Phase 2: Capacity Building | May – June | - Conduct Training of Trainers (ToT) for wardens and teachers - Train peer mentors - Prepare session kits and reusable IEC materials |
| Phase 3: Awareness Event + Starter Distribution | June – July | - Run a one-day menstrual health session in each school - Distribute starter kits (2–3 sanitary napkin packs per girl) |
| Phase 4: School-led Reinforcement | August – March | - Peer hygiene mentors and teachers revisit key messages during the year - Use visual materials to reinforce menstrual health messages - Encourage individual responsibility and healthy habits |
| Phase 5: Monitoring & Feedback | September – December (ongoing) | - Light-touch monitoring through phone check-ins, feedback slips, and occasional visits - End-of-year summary report with insights and recommendations for next cycle |

## 8. Budget Overview

## The Sthree Swabhiman initiative is designed to deliver an annual menstrual hygiene intervention across 275 girls-only MJPTBCWREIS residential schools and junior colleges in Telangana. The budgeting model is based on the actual enrollment estimate of approximately 1,23,000 adolescent girls, ensuring cost-efficiency and comprehensive coverage of the target group.

### 🔹 A. Budget Summary by Category

| ## Category | ## Details | ## Unit Cost (INR) | ## Quantity | ## Total Cost (INR) |
| --- | --- | --- | --- | --- |
| ## I. Product Cost |  |  |  |  |
| ## Sanitary Napkin Packs | ## 12 packs per girl per year | ## ₹45 | ## 1,23,000 girls × 12 packs | ## ₹66,42,0000 |
| ## II. Program Delivery Cost |  |  |  |  |
| ## Awareness Session Facilitation | ## One-day MHM awareness session | ## ₹10,000 | ## 275 schools/colleges | ## ₹27,50,000 |
| ## Training of Trainers (ToT) | ## Staff + peer mentor capacity building | ## ₹5,000 | ## 275 institutions | ## ₹13,75,000 |
| ## IEC Materials | ## Telugu handouts, flipbooks, posters | ## ₹3,000 | ## 275 institutions | ## ₹8,25,000 |
| ## Monitoring and Feedback | ## Follow-up, phone tracking, light supervision | ## ₹2,000 | ## 275 institutions | ## ₹5,50,000 |
| ## Total Project Cost (Annual) |  |  |  | ## ₹7,23,42,000 |

### 🔹 B. Key Budget Notes

## Total sanitary napkin packs distributed: 14,76,000 packs

## Cost per girl (product + delivery): approx. ₹588

## Estimates can be optimized through bulk procurement or CSR in-kind contributions

## Scalable model: institution-level delivery cost remains consistent

## 9. SDG Alignment and Strategic Benefits

The Sthree Swabhiman initiative directly contributes to India’s commitment toward achieving the United Nations Sustainable Development Goals (SDGs), particularly in the context of adolescent girls’ health, education, and dignity in rural and tribal settings.

### 🔹 A. Alignment with Key SDGs

| SDG | Goal Title | Contribution Through This Project |
| --- | --- | --- |
| SDG 3 | Good Health and Well-being | Promotes menstrual hygiene, reduces infections, and improves overall well-being of adolescent girls |
| SDG 4 | Quality Education | Reduces school absenteeism and dropout due to menstruation-related stigma or lack of sanitary products |
| SDG 5 | Gender Equality | Empowers girls with knowledge and dignity, challenges taboos, and ensures access to safe menstrual care |
| SDG 6 | Clean Water and Sanitation | Reinforces hygiene education and responsible product disposal practices |
| SDG 10 | Reduced Inequalities | Focuses on vulnerable groups — rural, tribal, and socially disadvantaged adolescent girls |
| SDG 17 | Partnerships for the Goals | Enables collaboration between government, NGOs, and CSR partners for scalable health interventions |

### 🔹 B. Strategic and Social Benefits

- Improved School Attendance: Girls are more likely to stay in school during their periods when they have access to sanitary products and are educated about menstrual health.

- Behavioral Change: Structured awareness sessions lead to increased comfort, self-confidence, and long-term hygiene habits.

- Capacity Building: Empowers school staff and senior students to carry forward the message year after year, making the model institutionally sustainable.

- Equity and Inclusion: Prioritizes adolescent girls from Scheduled Caste (SC), Scheduled Tribe (ST), and Other Backward Class (OBC) backgrounds, aligning with national inclusion policies.

- Cultural Sensitivity: Materials and training are designed in regional language (Telugu) and tailored to local beliefs to ensure acceptance and resonance.

### 10. Key Benefits and Outcomes

The Sthree Swabhiman initiative is designed to achieve tangible improvements in menstrual health awareness, hygiene practices, and dignity for adolescent girls studying in government residential institutions across Telangana. Beyond direct sanitary pad distribution, the program fosters long-term behavioral change, school-level capacity building, and empowerment.

### 🔹 A. Direct Benefits

| Area | Benefit |
| --- | --- |
| Health & Hygiene | Girls gain access to safe, hygienic menstrual care products, reducing infections and discomfort. |
| Awareness & Education | Myths and taboos around menstruation are challenged through structured, age-appropriate education. |
| School Attendance | Reduced menstruation-related absenteeism by ensuring girls feel confident and prepared. |
| Psychosocial Well-being | Enhanced self-esteem and dignity among adolescent girls. |

### 🔹 B. Institutional Outcomes

| Area | Outcome |
| --- | --- |
| Capacity Building | School wardens, teachers, and peer mentors are trained to sustain menstrual health programming annually. |
| Sustainable Delivery | Educational materials and tools remain in the school for reuse each academic cycle. |
| Operational Simplicity | One-time annual engagement model minimizes NGO overhead and encourages school ownership. |

### 🔹 C. Long-Term Social Impact

- Reduction in Period Shame: Encourages open conversations and normalizes menstrual health among girls and boys in school communities.

- Early Health Literacy: Equips girls with lifelong knowledge on reproductive health and self-care.

- Equity in Access: Prioritizes socially and economically disadvantaged girls, contributing to inclusive development.

- Community Ripple Effect: Girls become agents of change in their families and villages, spreading menstrual health awareness beyond school walls.

### 11. Key Performance Indicators (KPIs)

To ensure effective implementation and measurable outcomes, the Sthree Swabhiman initiative will track both quantitative and qualitative indicators. These KPIs will guide internal monitoring, help evaluate program success, and provide transparent reporting for CSR and institutional partners.

### 🔹 A. Implementation KPIs

| Indicator | Target / Measurement |
| --- | --- |
| Number of schools covered | 100% of planned schools per phase (e.g., 50 in pilot, 173 full-scale) |
| Number of girls reached | Based on actual school enrollment data (~1,01,000 total) |
| Number of awareness sessions conducted | 1 per school annually |
| Number of starter kits distributed | 12 napkin packs × total enrolled girls |
| Completion of ToT sessions | At least 2–3 staff/peer mentors trained per school |
| IEC material dissemination | Display and distribution in 100% of covered schools |

### 🔹 B. Outcome KPIs

| Indicator | Measurement Approach |
| --- | --- |
| % increase in girls using sanitary pads | Baseline vs. follow-up survey (sample-based) |
| Reduction in menstruation-related absenteeism | Pre- and post-intervention comparison (from school logs) |
| Feedback from girls on awareness session | Feedback forms / group discussions in sample schools |
| Feedback from school staff on program utility | Structured interviews or quick surveys |
| Reuse of IEC materials in subsequent cycles | Monitoring visit checks and follow-ups |

### 🔹 C. Impact Indicators (Long-Term)

| Indicator | How It’s Evaluated |
| --- | --- |
| Improved comfort and confidence levels | Focus group responses and teacher observations |
| Continued pad usage after program ends | Follow-up interviews with students (in Year 2) |
| School adoption of repeat sessions | % of schools repeating awareness sessions with minimal external input |

These KPIs will be tracked through a combination of school reporting, light-touch field monitoring, phone check-ins, and sample surveys. A year-end summary report will be generated to inform scale-up, highlight success stories, and capture lessons learned.

### 12. Monitoring and Evaluation (M&E) Framework

A robust Monitoring and Evaluation (M&E) framework is central to the success and sustainability of the Sthree Swabhiman initiative. The M&E plan is designed to ensure accountability, capture program impact, and continuously improve delivery by integrating real-time feedback and periodic assessments.

The framework balances light-touch monitoring for scalability with qualitative and quantitative tools for capturing behavioral and institutional change.

### 🔹 A. Objectives of M&E

- Track delivery efficiency across all program components (awareness sessions, kit distribution, staff training).

- Measure short- and medium-term outcomes among adolescent girls (product usage, hygiene awareness, attendance impact).

- Enable feedback-based improvements for future program cycles.

- Ensure transparency and reporting for CSR sponsors, school authorities, and government stakeholders.

### 🔹 B. M&E Activities by Program Phase

| Phase | Monitoring Activity | Method / Tool |
| --- | --- | --- |
| Pre-Implementation | Baseline data collection in sample schools (product use, absenteeism) | Surveys, focus groups, school records |
| During Implementation | Attendance records, distribution tracking, training session logs | NGO reporting forms, school checklists |
| Post-Session Feedback | Student and staff feedback on awareness sessions and materials | Feedback forms, group reflections |
| Quarterly Monitoring | Check-in calls with wardens, periodic site visits (sample basis) | Phone interviews, observation checklists |
| Year-End Evaluation | Summary report on reach, outcomes, lessons learned | Consolidated M&E report |

### 🔹 C. Tools and Roles

- Monitoring Tools:

  - Distribution registers for sanitary napkins

  - Awareness session attendance sheets

  - Standardized feedback forms (students and staff)

  - Sample survey templates for outcome indicators

- M&E Team:

  - NGO field coordinators will lead data collection

  - Trained school focal points (wardens/teachers) will support in-school tracking

  - A central M&E officer will compile and analyze results

### 🔹 D. Data Use and Reporting

- Annual M&E Report: Shared with funding partners, school administrators, and the Department of Samagra Shiksha.

- Insights for Improvement: Used to enhance program design, refine training modules, and support policy advocacy

- Documentation for Scale-Up: High-performing models and schools will be highlighted for replication across other districts

## 13. Sustainability Strategy

Ensuring that the Sthree Swabhiman initiative leaves behind a durable impact without creating prolonged external dependency is a core design principle. While sanitary napkin distribution is a key component, the program’s sustainability lies in its ability to institutionalize menstrual hygiene as a part of the school culture — through capacity building, education, and behavior change.

This section outlines a practical sustainability roadmap and a phased exit strategy, aligned with the realities of rural and tribal government residential schools.

### 🔹 A. Core Sustainability Pillars

| Pillar | Strategy for Longevity |
| --- | --- |
| 1. Institutional Ownership | School staff (wardens, teachers) and peer mentors are trained to independently deliver sessions each year. |
| 2. Reusable Educational Assets | Posters, charts, flipbooks, and training manuals in Telugu are left behind in schools for ongoing use. |
| 3. Behavior Change, Not Subsidy Dependence | Students are encouraged to adopt healthy hygiene habits and to make personal choices for continued sanitary product use. |
| 4. Curriculum Integration Potential | With state support, core menstrual hygiene messages can be integrated into health or science classes. |
| 5. Local Partnerships for Pad Access | Schools will be linked to local vendors or CSR-supported micro-entrepreneurs for pad supply beyond the initial year. |

### 🔹 B. Realistic Exit Strategy (3-Year Model)

The program is structured as a 3-year stepped exit model to gradually shift ownership to the schools while maintaining quality.

| Year | NGO Role | School Role |
| --- | --- | --- |
| Year 1 | Full implementation: sessions, distribution, training | Participate, observe, nominate mentors |
| Year 2 | Partial support: NGO runs sessions jointly with schools | School delivers with NGO guidance |
| Year 3 | Remote support only: refresher kits, call support | School independently runs session with student mentors |

### 🔹 C. Addressing Common Challenges & Realities

| Challenge | Response / Mitigation |
| --- | --- |
| High staff turnover in schools | Repeat ToT modules each year; train more than one focal person per school |
| Risk of pad dependency | Program emphasizes starter kits + choice education, not ongoing free provision |
| Budget limitations in government schools | Model enables low-cost self-sustained delivery after initial NGO involvement |
| Cultural taboos or reluctance | Uses local-language materials and peer role models to normalize the topic |
| Disruption due to academic calendar shifts | Flexible delivery window during June–July; regional rollout adaptability |

### 🔹 D. Long-Term Vision

The goal is not just product distribution, but the normalization of menstrual health in educational spaces. By Year 4 and beyond, the Sthree Swabhiman model will:

- Be fully owned and driven by schools

- Require no recurring NGO field presence

- Be eligible for state or CSR-led booster funding only when needed

- Serve as a replicable framework for other departments (e.g., Tribal Welfare, BC Welfare)

## 14. Conclusion and Strategic Appeal

Menstruation, though a natural and universal biological process, continues to limit the educational, social, and emotional well-being of thousands of adolescent girls across Telangana — especially those enrolled in rural and tribal government residential institutions.

Despite advancements in education and health, menstruation remains shrouded in silence, stigma, and misinformation. As a result, adolescent girls often face barriers to attending school, practicing safe hygiene, or even speaking openly about their own health needs.

The Sthree Swabhiman initiative seeks to transform this reality — turning menstruation from a barrier into a platform for empowerment, dignity, and resilience.

By embedding menstrual hygiene awareness, education, and starter support into the academic calendar of Kasturba Gandhi Balika Vidyalayas, this initiative ensures that every newly enrolled girl receives timely support — not just with sanitary products, but with the knowledge, confidence, and comfort to manage her menstrual health without fear or shame.

Strategic Appeal for Support

We invite CSR partners, philanthropic organizations, foundations, and social investors to join hands with us in normalizing menstruation and building dignity-centered schools.

Your support can help:

- Ensure that no adolescent girl misses school or suffers in silence because of her period.

- Build a generation of confident, health-literate young women, especially from underserved SC/ST and rural communities.

- Establish a replicable and scalable framework for menstrual hygiene education that can be extended to other government school networks across India.

### Our Shared Vision

With your partnership, we can normalize menstrual health as part of the school environment — where dignity, inclusion, and wellness are non-negotiable for every child.

Together, we can:

- Shatter stigma

- Restore confidence

- And make sure no girl is left behind because of her period.