# Sthree Swabhiman

## Menstrual Hygiene & Dignity Initiative for Girls in Educational Institutions

### For Mining-Affected Rural & Tribal Communities

### Jayashankar Bhupalpally District, Telangana

### Under District Mineral Foundation Trust (DMFT) / PMKKKY

Presented as: # MP Initiative under DMFT

Implementation Support: Give For Society

# SECTION 11 — DETAILED BUDGET FRAMEWORK

## Semi-DPR Financial Structure

The proposed Sthree Swabhiman initiative is designed as a district-level institutional menstrual hygiene and adolescent dignity infrastructure programme under the District Mineral Foundation Trust (DMFT) / PMKKKY framework.

The budget framework has been prepared based on:

- pilot phase implementation,

- institutional hygiene infrastructure strengthening,

- adolescent awareness systems,

- electric incinerator installation,

- starter hygiene support kits,

- and WASH strengthening interventions.

The proposed budget structure emphasizes: # Sustainable Institutional Hygiene Systems rather than recurring consumable subsidy models.

# FROZEN PHASE-1 IMPLEMENTATION MODEL

| Parameter | Approved Assumption |
| --- | --- |
| Implementation Model | Pilot + Expansion |
| Phase-1 Institutions | 25 Institutions |
| Average Girls per Institution | 400 |
| Estimated Direct Girl Beneficiaries | 10,000+ |
| Institution Categories | All approved categories |
| Implementation Duration | 2 Years |
| Pad Support Model | Awareness + Starter Kits |
| Incinerator Model | Small Electric Institutional Units |
| WASH Strengthening | Moderate |
| Geographic Coverage | Mining-Affected Mandals |

# SECTION A — MENSTRUAL HYGIENE AWARENESS PROGRAMMES

## Scope

District-level institutional awareness systems focused on:

- menstrual health,

- adolescent dignity,

- hygiene awareness,

- stigma reduction,

- and safe menstrual practices.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Awareness Sessions | 100 | ₹15,000 | ₹15,00,000 |
| Awareness Resource Materials | 10,000 girls | ₹150 | ₹15,00,000 |
| Training & IEC Materials | Lump Sum | — | ₹5,00,000 |
| Travel & Outreach Support | Lump Sum | — | ₹4,00,000 |
| Session Facilitation Costs | Lump Sum | — | ₹6,00,000 |

### Subtotal

# ₹45,00,000

# SECTION B — STARTER HYGIENE & DIGNITY KITS

## Scope

Provision of: # Menstrual Hygiene Starter Kits

for adolescent girls in participating institutions.

Each starter kit may include:

- sanitary pads,

- hygiene information materials,

- emergency hygiene supplies,

- disposal guidance materials.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Starter Hygiene Kits | 10,000 | ₹350 | ₹35,00,000 |
| Emergency Institutional Hygiene Reserve | 25 institutions | ₹20,000 | ₹5,00,000 |
| Distribution & Logistics | Lump Sum | — | ₹3,00,000 |

### Subtotal

# ₹43,00,000

# SECTION C — ELECTRIC INCINERATOR SYSTEMS

## Scope

Installation of: # Small Electric Institutional Incinerators

for safe menstrual waste disposal.

## Assumptions

| Parameter | Value |
| --- | --- |
| Institutions | 25 |
| Units per Institution | 1 |
| Incinerator Type | Small Electric Model |

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Electric Incinerators | 25 | ₹65,000 | ₹16,25,000 |
| Electrical Installation | 25 | ₹10,000 | ₹2,50,000 |
| Safety Signage & Usage Boards | 25 | ₹5,000 | ₹1,25,000 |
| Installation & Commissioning | 25 | ₹8,000 | ₹2,00,000 |
| Maintenance Provision (2 Years) | Lump Sum | — | ₹4,00,000 |

### Subtotal

# ₹26,00,000

# SECTION D — TOILET & WASH STRENGTHENING

## Scope

Moderate institutional WASH strengthening including:

- minor toilet repair,

- handwash systems,

- disposal bins,

- water access improvements,

- hygiene infrastructure.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Minor Toilet Repair | 25 institutions | ₹1,50,000 | ₹37,50,000 |
| Handwash Stations | 25 institutions | ₹40,000 | ₹10,00,000 |
| Disposal Bins & Systems | 25 institutions | ₹20,000 | ₹5,00,000 |
| Water Access Improvements | 25 institutions | ₹60,000 | ₹15,00,000 |
| Hygiene Signage & Awareness Displays | 25 institutions | ₹10,000 | ₹2,50,000 |

### Subtotal

# ₹70,00,000

# SECTION E — TRAINING & CAPACITY BUILDING

## Scope

Training systems for:

- teachers,

- wardens,

- institutional coordinators,

- and local implementation stakeholders.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Teacher/Warden Training Workshops | 25 | ₹20,000 | ₹5,00,000 |
| Training Materials | Lump Sum | — | ₹2,50,000 |
| Institutional Orientation Sessions | 25 | ₹10,000 | ₹2,50,000 |
| Capacity Building Support | Lump Sum | — | ₹3,00,000 |

### Subtotal

# ₹13,00,000

# SECTION F — MONITORING & IMPLEMENTATION SUPPORT

## Scope

Programme management, district coordination, monitoring, reporting, and implementation oversight.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| District Project Coordination | 24 Months | ₹75,000/month | ₹18,00,000 |
| Field Monitoring Visits | Lump Sum | — | ₹8,00,000 |
| Reporting & Documentation | Lump Sum | — | ₹5,00,000 |
| Data Collection & MIS | Lump Sum | — | ₹4,00,000 |
| Administrative Support | Lump Sum | — | ₹5,00,000 |

### Subtotal

# ₹40,00,000

# SECTION G — CONTINGENCY & EMERGENCY SUPPORT

| Component | Total |
| --- | --- |
| Contingency Reserve | ₹15,00,000 |

# PHASE-1 CONSOLIDATED BUDGET SUMMARY

| Component | Total |
| --- | --- |
| Awareness Programmes | ₹45,00,000 |
| Starter Hygiene Kits | ₹43,00,000 |
| Electric Incinerators | ₹26,00,000 |
| Toilet & WASH Strengthening | ₹70,00,000 |
| Training & Capacity Building | ₹13,00,000 |
| Monitoring & Implementation Support | ₹40,00,000 |
| Contingency Reserve | ₹15,00,000 |

# TOTAL ESTIMATED PHASE-1 BUDGET

# ₹2,52,00,000

## (₹2.52 Crores)

# COST POSITIONING UNDER DMFT

The proposed financial structure has been designed as: # Institutional Infrastructure + Adolescent Dignity Systems

rather than:

- recurring consumable subsidy expenditure.

This approach ensures:

- sustainability,

- administrative feasibility,

- infrastructure durability,

- and scalable district implementation.

# COST EFFICIENCY INDICATORS

| Indicator | Estimate |
| --- | --- |
| Cost per Institution | ~₹10 Lakhs |
| Cost per Girl Beneficiary | ~₹2,500 |
| Direct Girl Beneficiaries | 10,000+ |
| Institutional Infrastructure Coverage | 25 Institutions |

# IMPLEMENTATION PHASE STRUCTURE

| Phase | Timeline |
| --- | --- |
| Phase 1 | Institutional baseline assessment |
| Phase 2 | Procurement & installation |
| Phase 3 | Awareness & starter kit rollout |
| Phase 4 | WASH strengthening |
| Phase 5 | Monitoring & review |
| Phase 6 | Expansion planning |

# PROPOSED EXPANSION MODEL

Following successful Phase-1 implementation:

- additional institutions,

- district-wide expansion,

- and deeper WASH integration

may be considered under subsequent DMFT phases.

# FINANCIAL SUSTAINABILITY APPROACH

The initiative emphasizes:

- infrastructure-based intervention,

- awareness-led behavioural systems,

- institutional ownership,

- and limited recurring financial dependency.

This strengthens: # long-term sustainability and scalability within the district institutional ecosystem.