# Vidya Pragathi

## ZPHS Infrastructure, STEM & Digital Education Strengthening Initiative

### For Mining-Affected Rural & Tribal Government High Schools

### Jayashankar Bhupalpally District, Telangana

### Under District Mineral Foundation Trust (DMFT) / PMKKKY

Presented as: # MP Initiative under DMFT

Implementation Support: Give For Society

# SECTION 11 — DETAILED BUDGET FRAMEWORK

## Semi-DPR Financial Structure

The proposed Vidya Pragathi initiative is designed as a district-level government high school modernization and STEM strengthening programme under the District Mineral Foundation Trust (DMFT) / PMKKKY framework.

The budget framework has been prepared based on:

- STEM infrastructure strengthening,

- digital classroom modernization,

- school sanitation systems,

- educational infrastructure enhancement,

- library modernization,

- student wellness systems,

- and school-level digital inclusion.

The proposed financial structure emphasizes: # Permanent Educational Infrastructure Assets capable of generating long-term institutional impact across mining-affected rural and tribal government high schools.

# FROZEN PHASE-1 IMPLEMENTATION MODEL

| Parameter | Approved Assumption |
| --- | --- |
| Coverage Model | Pilot + Expansion |
| Target Institutions | ZPHS Only |
| Phase-1 School Coverage | 25 ZPHS Schools |
| STEM Lab Model | Moderate Functional Labs |
| Digital Classroom Model | Moderate Smart Classroom |
| Library Model | Moderate |
| WASH Model | Moderate Repair & Improvement |
| Furniture Model | Comprehensive |
| Sports Model | Basic Wellness-Oriented |
| Solar Model | Limited Backup Systems |
| Implementation Duration | 2 Years |
| Geographic Coverage | Mining-Affected & Tribal Mandals |

# SECTION A — STEM LAB INFRASTRUCTURE

## Scope

Establishment of: # Functional STEM Learning Infrastructure

including:

- Physics,

- Chemistry,

- Biology practical systems,

- demonstration models,

- safety systems,

- and lab furniture.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Physics Lab Equipment | 25 | ₹2,00,000 | ₹50,00,000 |
| Chemistry Lab Equipment | 25 | ₹2,25,000 | ₹56,25,000 |
| Biology Lab Equipment | 25 | ₹1,75,000 | ₹43,75,000 |
| STEM Demonstration Models | 25 | ₹50,000 | ₹12,50,000 |
| Lab Safety Equipment | 25 | ₹25,000 | ₹6,25,000 |
| Lab Furniture & Fixtures | 25 | ₹1,50,000 | ₹37,50,000 |

### Subtotal

# ₹2,06,25,000

# SECTION B — DIGITAL CLASSROOM SYSTEMS

## Scope

Implementation of: # Smart Classroom & Digital Learning Infrastructure

supporting:

- digital teaching,

- blended learning,

- smart classroom systems,

- and technology-enabled education.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Smart TVs / Projectors | 25 | ₹1,20,000 | ₹30,00,000 |
| Teacher Laptop Systems | 25 | ₹60,000 | ₹15,00,000 |
| Audio Systems | 25 | ₹20,000 | ₹5,00,000 |
| Internet Connectivity Setup | 25 | ₹25,000 | ₹6,25,000 |
| Digital Learning Software & Content | 25 | ₹40,000 | ₹10,00,000 |
| Installation & Configuration | 25 | ₹20,000 | ₹5,00,000 |

### Subtotal

# ₹71,25,000

# SECTION C — LIBRARY & LEARNING RESOURCE SYSTEMS

## Scope

Strengthening school learning ecosystems through:

- library modernization,

- books,

- reading systems,

- furniture,

- and academic learning support.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Academic Books & Learning Resources | 25 | ₹1,00,000 | ₹25,00,000 |
| Library Furniture & Shelving | 25 | ₹75,000 | ₹18,75,000 |
| Reading Tables & Chairs | 25 | ₹40,000 | ₹10,00,000 |
| Digital Learning Corner Setup | 25 | ₹50,000 | ₹12,50,000 |

### Subtotal

# ₹66,25,000

# SECTION D — TOILET & WASH INFRASTRUCTURE

## Scope

Moderate institutional sanitation strengthening including:

- toilet repair,

- girls sanitation systems,

- handwash infrastructure,

- drinking water support,

- and hygiene improvements.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Toilet Repair & Rehabilitation | 25 | ₹2,00,000 | ₹50,00,000 |
| Girls Sanitation Support Systems | 25 | ₹75,000 | ₹18,75,000 |
| Handwash Stations | 25 | ₹50,000 | ₹12,50,000 |
| Drinking Water Improvements | 25 | ₹75,000 | ₹18,75,000 |
| Hygiene Signage & Awareness Systems | 25 | ₹20,000 | ₹5,00,000 |

### Subtotal

# ₹1,05,00,000

# SECTION E — SCHOOL FURNITURE STRENGTHENING

## Scope

Classroom and learning environment strengthening through:

- dual desks,

- teacher furniture,

- lab furniture,

- and student learning infrastructure.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Student Dual Desk Benches | 25 schools | ₹2,00,000 | ₹50,00,000 |
| Teacher Furniture | 25 schools | ₹40,000 | ₹10,00,000 |
| Classroom Storage Units | 25 schools | ₹30,000 | ₹7,50,000 |
| Additional Learning Furniture | 25 schools | ₹50,000 | ₹12,50,000 |

### Subtotal

# ₹80,00,000

# SECTION F — SPORTS & STUDENT WELLNESS SYSTEMS

## Scope

Basic school-level student wellness and sports support systems.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Multi-Sport Kits | 25 | ₹50,000 | ₹12,50,000 |
| Indoor Games & Wellness Equipment | 25 | ₹20,000 | ₹5,00,000 |
| Playground Activity Support | 25 | ₹30,000 | ₹7,50,000 |

### Subtotal

# ₹25,00,000

# SECTION G — SOLAR BACKUP SYSTEMS

## Scope

Limited solar backup systems supporting:

- digital classrooms,

- STEM systems,

- and essential educational infrastructure continuity.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Limited Solar Backup Systems | 25 | ₹1,25,000 | ₹31,25,000 |
| Installation & Electrical Integration | 25 | ₹25,000 | ₹6,25,000 |

### Subtotal

# ₹37,50,000

# SECTION H — IMPLEMENTATION, MONITORING & DISTRICT COORDINATION

## Scope

Programme implementation support, district coordination, technical supervision, monitoring, reporting, and documentation.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| District Project Coordination | 24 Months | ₹75,000/month | ₹18,00,000 |
| Technical Monitoring Visits | Lump Sum | — | ₹10,00,000 |
| Reporting & Documentation | Lump Sum | — | ₹6,00,000 |
| Data Collection & MIS | Lump Sum | — | ₹5,00,000 |
| Administrative Support | Lump Sum | — | ₹6,00,000 |

### Subtotal

# ₹45,00,000

# SECTION I — CONTINGENCY RESERVE

| Component | Total |
| --- | --- |
| Contingency Reserve | ₹25,00,000 |

# PHASE-1 CONSOLIDATED BUDGET SUMMARY

| Component | Total |
| --- | --- |
| STEM Lab Infrastructure | ₹2,06,25,000 |
| Digital Classroom Systems | ₹71,25,000 |
| Library & Learning Systems | ₹66,25,000 |
| Toilet & WASH Infrastructure | ₹1,05,00,000 |
| School Furniture Strengthening | ₹80,00,000 |
| Sports & Wellness Systems | ₹25,00,000 |
| Solar Backup Systems | ₹37,50,000 |
| Monitoring & Coordination | ₹45,00,000 |
| Contingency Reserve | ₹25,00,000 |

# TOTAL ESTIMATED PHASE-1 BUDGET

# ₹6,61,25,000

## (₹6.61 Crores)

# COST POSITIONING UNDER DMFT

The proposed financial structure has been designed as: # Long-Term Educational Infrastructure Modernization

focused on:

- durable public educational assets,

- STEM learning systems,

- digital inclusion,

- sanitation infrastructure,

- and institutional strengthening.

This approach ensures:

- sustainability,

- infrastructure durability,

- and long-term educational impact.

# COST EFFICIENCY INDICATORS

| Indicator | Estimate |
| --- | --- |
| Cost per School | ~₹26 Lakhs |
| Direct Student Beneficiaries | 25,000+ |
| STEM Infrastructure Coverage | 25 Schools |
| Digital Classroom Coverage | 25 Schools |
| WASH Infrastructure Coverage | 25 Schools |

# IMPLEMENTATION PHASE STRUCTURE

| Phase | Timeline |
| --- | --- |
| Phase 1 | School baseline assessment |
| Phase 2 | Procurement & vendor onboarding |
| Phase 3 | STEM & digital infrastructure installation |
| Phase 4 | WASH & furniture strengthening |
| Phase 5 | School activation & training |
| Phase 6 | Monitoring & district review |

# PROPOSED EXPANSION MODEL

Following successful Phase-1 implementation:

- additional ZPHS schools,

- advanced STEM systems,

- expanded digital learning,

- and district-wide educational modernization

may be considered under future DMFT phases.

# FINANCIAL SUSTAINABILITY APPROACH

The initiative emphasizes:

- institutional infrastructure strengthening,

- durable educational assets,

- digital continuity,

- and school ecosystem modernization.

This strengthens: # long-term sustainability and scalable government school modernization across mining-affected rural and tribal communities.