AROGYASETU

Mobile Health and Community Well-being Initiative for Tribal Telangana

Detailed Project Report — CSR Funding Proposal

Give For Society  •  Adilabad • Kumuram Bheem Asifabad • Mulugu • Mancherial • Bhadradri Kothagudem

| 10,000+ People Served / Year | 4 Tribal Districts | 2 Mobile Health Vans | 50+ Villages Covered |
| --- | --- | --- | --- |

Give For Society • Reg. No. 1255/2017 • 12A & 80G Certified • Telangana Governor’s Excellence Award 2025

1.  Executive Summary

In the tribal belts of Adilabad, Kumuram Bheem Asifabad, Mulugu, Mancherial, and Bhadradri Kothagudem districts, a preventable health gap quietly widens. Primary health centres are understaffed and under-equipped. Pregnant women go unscreened. Adolescent girls manage menstruation without products, knowledge, or safe disposal. Chronic conditions — hypertension, diabetes, anaemia — go undetected until they become crises.

ArogyaSetu (Bridge to Health) is Give For Society’s structured response to this. It is a mobile, community-grounded health initiative that brings preventive healthcare, maternal and child health support, menstrual hygiene awareness, and telemedicine to the doorstep of tribal and rural communities in Telangana — where the absence of these services is not an oversight but a structural gap that has persisted for decades.

The programme operates through two mobile health vans, a district telemedicine hub, community health camps, and menstrual hygiene awareness sessions in tribal villages and habitations. All service delivery is coordinated with district health departments, PHCs, and ASHA workers — so that ArogyaSetu strengthens the public health system rather than running parallel to it.

ArogyaSetu is proposed as a 12-month pilot covering 50+ villages across five tribal ITDA districts, reaching approximately 10,000 individuals with preventive screenings, 1,000 pregnant women with anemia prevention support, and 5,000 non-practitioner women and girls across 50 villages with MHM starter kits (12 packs each, covering 6–12 months). The total CSR investment for the pilot year is ₹1,27,50,000 (INR One Crore, Twenty-Seven Lakhs and Fifty Thousand).

2.  Context and Need

The Tribal Health Gap in Telangana

Telangana’s five ITDA districts — Adilabad, Kumuram Bheem Asifabad, Mulugu, Mancherial, and Bhadradri Kothagudem — are home to a significant ST population, many living in interior forest habitations several kilometres from the nearest PHC or town. Despite the state’s overall health infrastructure improvements, these communities continue to face conditions that are fundamentally different from urban and peri-urban Telangana.

| Health Challenge | Situation in Target Districts |
| --- | --- |
| Anemia in Women | NFHS-5 data shows anemia prevalence among women aged 15–49 in Telangana at 57% — among the highest nationally. In tribal districts, rates are significantly higher due to nutritional deficiencies and poor antenatal care. |
| Maternal & Child Health | Adilabad and Kumuram Bheem Asifabad report below-state-average institutional delivery rates and high rates of low birth weight, directly linked to undetected maternal anaemia and inadequate antenatal screening. |
| Menstrual Hygiene | Adolescent girls in tribal habitations have limited or no access to sanitary products. Most use cloth, which is washed and reused in unsanitary conditions. Menstruation-related school absenteeism is estimated at 4–5 days per month. |
| Chronic Disease | Hypertension, diabetes, dental disease, and vision impairment are widespread but largely undiagnosed in tribal areas due to absence of regular screening. Most cases present at advanced stages. |
| Healthcare Access | PHCs in forested interior zones lack diagnostic equipment, trained staff, and reliable drug supplies. Transportation to district hospitals costs a family multiple days’ wage. |

What these communities need is not another fixed health facility — the infrastructure backlog is too large and too slow to fill. What they need is a service model that comes to them, integrates with existing government machinery, and builds lasting community health capacity. ArogyaSetu is designed around exactly that principle.

3.  Programme Design

ArogyaSetu is structured around four integrated components. Each is designed to work independently but is most effective when delivered as part of the combined programme.

Component A — Mobile Health Vans and Village Health Camps

Two fully equipped mobile health vans will operate on fixed weekly routes across 50+ villages and habitations in the four target districts. Each van is staffed per NHM Mobile Medical Unit guidelines: one Medical Officer (MBBS), one GNM Nurse, one Lab Technician, one Pharmacist-cum-Administrative Assistant, and one Driver-cum-Support Staff. The van carries portable diagnostic equipment, a point-of-care lab kit, a three-month stock of essential medicines sourced from the nearest government facility or warehouse, and a basic drug dispensing unit. The van visits each village on a scheduled day, so communities know when to expect it and can plan accordingly.

Services delivered at every camp:

- Blood pressure screening and hypertension management

- Diabetes screening (glucometer)

- Haemoglobin and anaemia screening

- Dental examination and basic oral health advice

- Vision screening and referral

- ECG for adults above 40

- Basic bloodwork (where feasible) and drug dispensing

- Referral to PHC/district hospital for cases requiring follow-up

Van staffing, scheduling, and routing are coordinated with the District Health Officer and PHC medical officers, following NHM MMU Operational Guidelines. Each village is visited on the same day of the month, every month — ensuring predictability and community trust. Routes are planned to prioritise habitations more than 5 km from the nearest functional PHC and village clusters served by weekly markets (Haats) to maximise footfall. ASHA workers and ANMs are briefed ahead of each camp, using the published monthly schedule, to mobilise the community and prioritise pregnant women, children under 5, and those with chronic conditions. The van carries a logbook maintained by the driver and supervised by the Medical Officer, available for verification by the District Health Society. GPS tracking is enabled on both vans. All services are free at the point of care. A grievance redressal telephone number is displayed on both vans. Patient confidentiality is maintained during all examinations. Each prescription includes the tentative date of the next MMU visit for follow-up continuity.

Component B — Maternal and Child Health Support

Anaemia in pregnancy is the single largest contributor to maternal and neonatal mortality in tribal Telangana’s ITDA districts. ArogyaSetu addresses this through a dedicated antenatal track embedded within the mobile health camp model.

- Haemoglobin screening for all pregnant women at each camp visit

- Distribution of 1,000 Anaemia Prevention Kits (iron-folic acid supplements, calcium, Vitamin D) to identified at-risk pregnant women

- One-on-one nutrition counselling for expectant mothers by the nurse/compounder

- Birth preparedness counselling and institutional delivery promotion

- Integration with ASHA worker follow-up for continued monitoring

- Electronic Health Record (EHR) entry for each registered pregnant woman, enabling follow-up tracking across camp visits

Component C — Menstrual Hygiene Awareness in Tribal Communities

The menstrual hygiene component of ArogyaSetu is focused on tribal villages and habitations — not institutional campuses (which are addressed under Give For Society’s separate Sthree Swabhiman programme). The approach here is community outreach: structured awareness sessions in villages, habitations, and tribal hamlets, with sample sanitary napkin distribution to demonstrate products and encourage adoption.

- 50 community menstrual hygiene awareness sessions in tribal villages across the five ITDA districts

- Sessions led by female health workers (ASHAs, ANMs) trained by Give For Society — ensuring cultural and linguistic appropriateness

- Content covers the menstrual cycle, safe hygiene practices, available products, myth-busting, and disposal

- Sample sanitary napkin kits distributed at each session (one pack per participant) to overcome the adoption barrier

- IEC materials in Telugu — illustrated flipbooks and wall posters — left in each habitation for ongoing reference

- Coordination with Gram Panchayat and AWC (Anganwadi Centre) for venue, mobilisation, and follow-through

Component D — Telemedicine Hub and Referral Management

A district-level telemedicine hub will provide specialist consultations for cases identified by the mobile vans that require follow-up beyond the generalist doctor on the van. The hub operates as a spoke in an existing public health network — not as a replacement for it.

- Hub setup at a central district location (Adilabad or Asifabad town) with a trained coordinator and stable internet connection

- Cases flagged by mobile van doctor are referred to hub coordinator who schedules teleconsultation with specialist (dermatologist, gynaecologist, ophthalmologist, or general physician)

- Teleconsultations conducted via a standard video platform (NHA’s e-Sanjeevani or equivalent approved MoHFW platform)

- Referral management for serious cases: coordination with district hospital admission, transport support (coordination with 108 where applicable)

- Case closure tracking: every referred case is followed up until resolution — treatment received, or referred upward

- Monthly telemedicine log shared with District Health Officer as part of programme reporting

4.  Target Geography and Communities

| District | Mandals / Areas | Community Profile |
| --- | --- | --- |
| Mulugu | Utnoor, Kerameri, Tiryani, Indervelli | Gond, Kolam, Andh tribes — scheduled areas, dense forest habitations, lowest health indicators in Telangana |
| Kumuram Bheem Asifabad | Asifabad, Wankidi, Sirpur, Kagaznagar | Gond, Pardhan, Kolam tribes — Kumuram Bheem district, ITDA Asifabad area, high anaemia and maternal mortality |
| Mulugu | Mahadevpur, Palimela | Koya, Nayakpod tribes — ITDA Eturnagaram area, forest habitations in erstwhile Warangal |
| Kotthagudem & Bhadradri | Eturnagaram, Venkatapur, Mangapet | Lambada, Koya communities in tribal mandals of Mancherial and Bhadradri Kothagudem — coal belt tribal habitations |

The programme specifically targets the final mile — habitations that are more than 5 km from the nearest PHC or town and are not consistently reached by existing government outreach. Van routes are designed in consultation with ASHA supervisors and PHC medical officers to maximise coverage of underserved habitations.

5.  Implementation Plan

| Phase | Timeline | Key Activities |
| --- | --- | --- |
| Phase 1 Setup | Months 1–2 | Van procurement, fit-out, and branding per NHM MMU colour code and “National Mobile Medical Unit” nomenclature (Model C: NGO-managed CAPEX and OPEX; essential drugs sourced from government warehouse). Recruitment of medical team (doctor, nurse, driver per van). Telemedicine hub setup and e-Sanjeevani registration. Route planning with District Health Officer, PHC MOs, and ASHA supervisors. MoU with District Collectors, Adilabad and Mulugu districts (in progress); existing MoU with District Collector, Jangaon for coordination. Baseline needs assessment in 50 target villages. ASHA and AWC orientation sessions. |
| Phase 2 Health Camps | Months 2–6 | Mobile van operations begin: 4 villages per week per van = 32 village camps/month. Preventive screenings (BP, diabetes, ECG, vision, dental). Anemia kit distribution to identified pregnant women. EHR data entry for all screened individuals. Weekly coordination call with PHC MO per route. |
| Phase 3 MHM Outreach | Months 3–5 | 50 menstrual hygiene awareness sessions in tribal habitations. ASHA-led sessions in Telugu with GFS facilitator support. Sample napkin kit distribution at each session. IEC materials placed in each habitation. Session data and attendance recorded. |
| Phase 4 Telemedicine | Months 2–12 | Hub operational from Month 2. Target: 200+ teleconsultations per month. Case referral tracking maintained in shared dashboard. Escalation to district hospital managed by hub coordinator. Monthly report to District Health Officer. |
| Phase 5 Monitoring | Months 4–12 | Quarterly field audits of all 4 districts. EHR dashboard review. MHM follow-up visits to 10 sample habitations. Anemia re-screening for kit recipients at 6 months. Year-end impact evaluation report to CSR partner. |

6.  Budget and Costing

6.1  One-Time Capital Costs

| Item | Qty | Amount (₹) |
| --- | --- | --- |
| Mobile Health Van (fully fitted, with AC, stretcher, storage) | 2 vans | ₹32,00,000 |
| Portable diagnostic equipment per van (BP, glucometer, ECG, vision, dental kit, haemoglobin analyser) | 2 sets | ₹6,00,000 |
| Telemedicine hub setup (tablet, camera, internet device, furniture) | 1 hub | ₹27,00,000 |
| Van branding, signage, and livery | 2 vans | ₹1,00,000 |
| EHR software setup and configuration (cloud subscription Year 1) | Lump sum | ₹1,20,000 |
| Initial drug kit and consumables stock | 2 kits | ₹27,00,000 |
| Sub-total A — Capital Costs |  | ₹43,20,000 |

6.2  Annual Recurring Costs (12 Months)

| Item | Coverage | Amount (₹) |
| --- | --- | --- |
| Medical team salaries (2 MOs + 2 GNM Nurses + 2 Lab Technicians + 2 Pharmacists + 2 Drivers) | 12 months | ₹27,00,000 |
| Telemedicine hub coordinator salary | 12 months | ₹3,60,000 |
| GFS programme coordinator | 12 months | ₹3,00,000 |
| Fuel, maintenance, and vehicle running costs (2 vans) | 12 months | ₹8,40,000 |
| Drugs, diagnostic consumables, and refills | 12 months | ₹4,20,000 |
| Anaemia Prevention Kits (iron, folic acid, calcium, Vit D) | 1,000 kits | ₹3,00,000 |
| MHM awareness sessions + intake screening (50 villages) | 50 sessions × 1 ASHA + GFS coordinator | ₹2,50,000 |
| Starter napkin kits — targeted non-practitioners (120 women/village × 12 packs × ₹45) | 50 villages × 100 women & girls × 12 packs | ₹27,00,000 |
| IEC materials — Telugu flipbooks and wall posters | 50 habitations | ₹1,00,000 |
| EHR cloud subscription renewal and data management | Annual | ₹60,000 |
| Monitoring, field visits, and impact evaluation | Quarterly | ₹3,00,000 |
| Reporting, documentation, and CSR compliance | Annual | ₹1,00,000 |
| Contingency (5%) | Overall | ₹2,80,000 |
| Sub-total B — Annual Recurring Costs |  | ₹84,30,000 |

TOTAL YEAR 1 INVESTMENT (Capital + Recurring) ₹1,27,50,000 (INR One Crore, Twenty-Seven Lakhs and Fifty Thousand Only) • Cost per beneficiary (health screening): ₹133 • 10,000+ individuals screened • 6,000+ women receiving MHM starter kits

From Year 2, capital costs are eliminated. Annual recurring cost (without depreciation) is approximately ₹84,30,000 — reducing cost per beneficiary to under ₹60 per person served.

7.  SDG Alignment and Schedule VII Compliance

| SDG | How ArogyaSetu Contributes |
| --- | --- |
| SDG 3 — Good Health | Mobile van screenings detect hypertension, diabetes, and anaemia before they become crises. Maternal health support reduces antenatal mortality risk in tribal districts. |
| SDG 4 — Quality Education | Menstrual hygiene awareness and sample kit distribution directly reduce the 4–5 days of monthly absenteeism that tribal girls experience. |
| SDG 5 — Gender Equality | Structured MHM sessions in tribal communities give women and adolescent girls knowledge, voice, and access they currently lack. |
| SDG 6 — Sanitation | Community awareness sessions include safe menstrual waste disposal practices in settings without formal waste infrastructure. |
| SDG 10 — Reduced Inequalities | Exclusively targets five tribal ITDA districts of Telangana with the worst health access indicators in the state. |
| SDG 16 — Strong Institutions | EHR and telemedicine data reported to District Health Officer, strengthening the public health data infrastructure. |

Schedule VII Compliance: This programme is eligible under Clause (i) — promoting health care including preventive health care; Clause (ii) — promoting education (school health and menstrual hygiene); and Clause (iii) — promoting gender equality and women’s empowerment. It also aligns with Swachh Bharat Mission and Poshan Abhiyaan (National Nutrition Mission).

8.  Monitoring and Reporting

| Indicator | Target (Year 1) |
| --- | --- |
| Individuals screened at mobile health camps | 10,000+ |
| Pregnant women receiving anaemia prevention kits | 1,000 |
| Teleconsultations through telemedicine hub | 2,400+ (200/month) |
| Villages covered by mobile van routes | 50+ |
| MHM community awareness sessions conducted | 50 |
| Girls/women attending MHM sessions | 2,500+ |
| Sample napkin kits distributed | 5,000 women & girls × 12 packs |
| Cases referred and tracked to resolution | 500+ |
| EHR records created | 10,000+ |

CSR partners receive: monthly programme update reports; quarterly field visit reports with photographic evidence; EHR dashboard access for real-time beneficiary data; a year-end impact evaluation report; and complete Schedule VII compliance documentation including utilisation certificates and district-level data.

9.  About Give For Society

| Organisation - Give For Society - Reg. No. 1255/2017, Telangana - 12A & 80G Certified — CSR eligible - Enrolled MP-LADS Implementing Agency | Government Credentials - MoU — District Collector, Jangaon - MoU — District Collector, Mulugu - MoC — MJPTBCWREIS (Lr.No.C2/3357/2025) - MoC — TMREIS (Minority Welfare) |
| --- | --- |

★  Telangana Governor’s Excellence Award 2025 — Corporate Volunteering, Organisation Category  ★

Conferred by Hon’ble Governor Shri Jishnu Dev Varma • 77th Republic Day • Lok Bhavan, Hyderabad

Track Record: School infrastructure (science labs, ICT labs, toilets) across Jangaon District under MP-LADS; Sthree Swabhiman MHM programme (pilot: November 2025, Warangal, 1,200+ students); ongoing ILC (Integrated Learning Centres) in rural and tribal Telangana’s ITDA districts.

10.  Conclusion

ArogyaSetu is not built on aspiration alone. It is built on a real gap in a real place, with a real model that has been designed to integrate with — not bypass — the public health system. The mobile vans do not compete with PHCs; they feed them. The telemedicine hub does not replace specialists; it connects communities to them. The menstrual hygiene sessions do not duplicate institutional programmes; they reach the women who are not in institutions.

For a CSR partner, ArogyaSetu offers something that is both visible and lasting: branded mobile health vans reaching over 50 villages every week; an EHR system tracking 10,000+ beneficiaries in real time; a telemedicine hub that keeps working year-round; and a menstrual hygiene programme that reaches women who have never had this conversation before.

A ₹1,27,50,000 investment in ArogyaSetu reaches 10,000+ people in tribal Telangana’s ITDA districts — with preventive healthcare, maternal health support, and menstrual hygiene education — in the first GFS_Unified_CSR_Proposal (1).pdfyear alone.