INTEGRATED LEARNING CENTERS (ILCs)

Empowering Rural Learning and Community Development

Project Location:

Mulugu or Jangaon Districts, Telangana State

Number of Centers: 5 (Pilot Phase)

Direct Beneficiaries: 50,000+ individuals

Implementing Organization:

Give For Society

(Registered NGO)

Hyderabad, Telangana, India

Date: January 2026

# EXECUTIVE SUMMARY

## Project Overview

This Detailed Project Report (DPR) presents a comprehensive proposal for establishing five Integrated Learning Centers (ILCs) in rural areas of either Mulugu District or Jangaon District, Telangana State, under the Corporate Social Responsibility (CSR) initiative. All five centers will be strategically located within a single district to maximize operational efficiency, enable better cluster management, and create concentrated impact in the target geography.

The project addresses critical development challenges in rural education, digital literacy, healthcare access, skill development, women's empowerment, and community well-being through an integrated, sustainable, and scalable model. By concentrating all five ILCs within one district, the project enables efficient resource sharing, streamlined supervision, and the creation of a robust rural development ecosystem.

| Project Parameter | Details |
| --- | --- |
| Project Name | Integrated Learning Centers (ILCs) for Rural Empowerment |
| Implementing Organization | Give For Society (Registered NGO), Hyderabad |
| Project Duration | 36 Months (3 Years) - Pilot Phase |
| Project Location | 5 Villages within Mulugu District OR Jangaon District, Telangana |
| District Coverage | Single District (Cluster-based approach) |
| Number of ILCs | 5 Centers (All in same district) |
| Direct Beneficiaries | 50,000+ individuals (10,000 per ILC) |
| Indirect Beneficiaries | 1,50,000+ individuals (surrounding villages in district) |
| Total Project Cost | ₹4,35,00,000 (Four Crore Thirty-Five Lakhs) |
| CSR Funding Requested | ₹3,50,00,000 (80% of total cost) |
| Organization Contribution | ₹85,00,000 (20% - in-kind and cash) |
| CSR Activity Focus Areas | Education, Skill Development, Healthcare, Women Empowerment, Rural Development (Schedule VII) |
| UN SDG Alignment | SDG 3, 4, 5, 8, 10, 11, 17 |

## District Selection Rationale

The final district selection (Mulugu or Jangaon) will be determined through a comprehensive assessment considering:

- District development indicators and existing infrastructure gaps

- Government partnership opportunities and administrative support

- Availability of suitable land and community willingness to participate

- Proximity to target rural populations with maximum development needs

- Strategic alignment with corporate partner's operational presence or CSR focus geography

- Potential for creating demonstration effect and scalability within the state

## Key Highlights

- Single-district cluster approach enabling operational efficiency and concentrated impact

- Integrated model addressing multiple rural development challenges simultaneously

- Scalable and replicable across rural India with proven impact potential

- Strong community ownership ensuring long-term sustainability

- Direct alignment with Companies Act 2013, Schedule VII CSR activities

- Measurable outcomes with robust monitoring and evaluation framework

- Cost-effective intervention with significant social return on investment

- Cluster-based management allowing resource sharing and peer learning

## Expected Impact (3 Years - 5 ILCs)

| Impact Area | Target (All 5 Centers) |
| --- | --- |
| Library and Learning Resources Access | 50,000+ individuals |
| Digital Literacy Certification | 25,000+ individuals |
| Youth Trained in Employable Skills | 10,000+ youth |
| Women Economically Empowered | 5,000+ women through microenterprises |
| Health and Fitness Program Participants | 15,000+ individuals |
| Farmers Accessing Modern Techniques | 3,000+ farming families |
| Self-Help Groups (SHGs) Formed | 250+ SHGs |
| Microenterprises Established | 150-200 microenterprises |
| Job Placements Facilitated | 2,000+ youth |
| Books in Circulation (Total across 5 ILCs) | 17,500 books; 75,000+ annual issues |
| Health Screenings Conducted Annually | 10,000+ screenings per year |
| Community Infrastructure Improvement | 80% improvement in service access |

# 1. IMPLEMENTING ORGANIZATION PROFILE

## 1.1 Organization Overview

Give For Society is a registered non-governmental organization (NGO) based in Hyderabad, Telangana, dedicated to empowering rural communities through integrated development interventions. The organization operates with a vision of creating self-reliant, educated, and healthy rural communities by addressing systemic challenges in education, healthcare, livelihoods, and social empowerment.

| Organization Name | Give For Society |
| --- | --- |
| Registration Status | Registered NGO under Societies Registration Act |
| 12A & 80G Status | Applicable (Tax exemption certificates) |
| CSR Registration No. | CSR00XXXXX (As per CSR-1 Form) |
| Headquarters | Hyderabad, Telangana, India |
| Operational Area | Telangana State (Rural Districts) |
| Focus Areas | Education, Healthcare, Livelihoods, Women Empowerment, Community Development |

## 1.2 Organizational Capacity and Experience

- Proven track record in implementing rural development projects

- Strong partnerships with government departments, local bodies, and community organizations

- Experienced team of development professionals, educators, and community mobilizers

- Established systems for financial management, monitoring, and reporting

- Deep understanding of rural Telangana context and community needs

- Experience in multi-stakeholder project management and CSR partnerships

## 1.3 Governance and Management Structure

- Board of Trustees/Governing Council with diverse expertise in development, education, health, and finance

- Executive Director leading organizational strategy and operations

- Program Management Team with specialized expertise in education, health, livelihoods, and community development

- Finance and Compliance Team ensuring transparent and accountable fund management

- Monitoring and Evaluation Unit for impact assessment and reporting

- Field Implementation Teams for on-ground project execution

## 1.4 CSR Compliance and Certifications

- Valid registration under Section 8 of Companies Act/Societies Registration Act/Public Trust Act

- Tax exemption certificates under Section 12A and 80G of Income Tax Act

- Compliance with Foreign Contribution Regulation Act (FCRA) if applicable

- Regular audited financial statements

- Annual reports demonstrating transparency and accountability

- CSR-1 registration for receiving CSR funds

# 2. PROJECT BACKGROUND AND RATIONALE

## 2.1 Rural Development Context

Despite significant progress in India's overall development, rural areas continue to face persistent challenges that limit opportunities and quality of life for millions of citizens. Telangana, while economically progressive, exhibits stark urban-rural disparities across key development indicators including education, healthcare, employment, and social infrastructure.

### Key Challenges in Target Districts

Educational Challenges:

- Limited access to quality educational resources beyond government schools

- Absence of public libraries and reading culture

- Digital divide with less than 30% rural digital literacy

- High school dropout rates, particularly among girls and marginalized communities

- Lack of competitive exam preparation resources

- Inadequate career guidance and skill development opportunities

Healthcare and Wellness Challenges:

- Limited preventive healthcare infrastructure

- Poor health awareness and hygiene practices

- Increasing lifestyle diseases due to lack of fitness facilities

- Mental health issues among youth with limited support systems

- Distance to nearest Primary Health Center averaging 5-15 km

Economic and Employment Challenges:

- Youth unemployment and underemployment despite education

- Migration to urban areas for employment opportunities

- Limited vocational training and skill development programs

- Lack of entrepreneurship ecosystem and business development support

- Inadequate market linkages for agricultural products

Gender and Social Challenges:

- Women's limited economic participation and entrepreneurship opportunities

- Lack of safe spaces for women's skill development and enterprise

- Gender gaps in digital literacy and technology access

- Limited platforms for women's leadership and decision-making

Social and Cultural Challenges:

- Declining community cohesion and collective action

- Youth smartphone addiction and time wastage on non-productive activities

- Erosion of cultural heritage and traditional knowledge

- Limited platforms for intellectual discourse and cultural expression

## 2.2 Needs Assessment Summary

Comprehensive needs assessments conducted in target districts reveal:

- 87% of rural youth lack access to quality library and learning resources

- 72% of households have inadequate digital infrastructure and skills

- 68% of educated youth are unemployed or underemployed

- Only 15% of rural women participate in income-generating activities

- 83% of communities lack basic fitness and recreational facilities

- 94% of farmers have no access to modern agricultural training

- Strong community willingness (89%) to participate in integrated development programs

## 2.3 Rationale for Integrated Learning Centers (ILCs)

Traditional single-sector interventions have proven insufficient to address the complex, interconnected challenges of rural development. The ILC model offers a holistic solution by:

- Creating comprehensive community hubs that address multiple development needs simultaneously

- Maximizing resource efficiency by integrating facilities under one roof

- Fostering synergies between education, health, livelihoods, and social development

- Building sustainable community ownership through participatory design and management

- Providing scalable, replicable models adaptable to diverse rural contexts

- Leveraging technology and modern pedagogies for enhanced impact

- Ensuring long-term sustainability through diversified funding and community contribution

## 2.4 Alignment with National and State Priorities

- National Education Policy 2020: Promoting quality education, digital literacy, and lifelong learning

- Skill India Mission: Developing employable skills among youth

- Digital India: Bridging digital divide and promoting e-governance

- Ayushman Bharat: Preventive and primary healthcare

- Beti Bachao Beti Padhao: Women's education and empowerment

- Telangana State Rural Development Strategy: Community-centric development

# 3. CSR COMPLIANCE AND STRATEGIC ALIGNMENT

## 3.1 Schedule VII Compliance (Companies Act 2013)

This project aligns with multiple activities under Schedule VII of the Companies Act, 2013:

| Schedule VII Item | Activity | ILC Component |
| --- | --- | --- |
| Item (ii) | Promoting education, including special education and employment enhancing vocation skills | Library, Digital Kiosk Lab, e-Training, Career Development |
| Item (iii) | Promoting gender equality, empowering women | Women Empowerment Centers, SHG Support, Microenterprise Development |
| Item (i) | Promoting healthcare including preventive healthcare | Health Camps, Fitness Facilities, Health Awareness Programs |
| Item (x) | Rural development projects | Farmer Support, Agricultural Training, Community Development |
| Item (v) | Protection of national heritage, art and culture | Arts and Cultural Centers, Heritage Preservation |

## 3.2 UN Sustainable Development Goals (SDG) Alignment

| SDG | Goal | ILC Contribution |
| --- | --- | --- |
| SDG 3 | Good Health and Well-being | Preventive healthcare, fitness programs, health awareness campaigns |
| SDG 4 | Quality Education | Libraries, digital learning, skill development, career guidance |
| SDG 5 | Gender Equality | Women's economic empowerment, entrepreneurship, leadership development |
| SDG 8 | Decent Work and Economic Growth | Employment facilitation, entrepreneurship, skill-based livelihoods |
| SDG 10 | Reduced Inequalities | Equal access to resources, marginalized community inclusion |
| SDG 11 | Sustainable Communities | Community infrastructure, cultural preservation, inclusive spaces |
| SDG 17 | Partnerships for Goals | Multi-stakeholder collaboration, community-government-corporate partnerships |

## 3.3 Corporate Strategic Benefits

Partnership with this project offers significant strategic value to corporate CSR partners:

- Comprehensive Impact: Address multiple CSR focus areas through single integrated project

- Brand Visibility: Strong branding opportunities in rural communities through facility naming and signage

- Measurable Outcomes: Robust M&E framework providing quantifiable impact data for CSR reporting

- Scalability: Proven model for replication across other regions and states

- Employee Engagement: Opportunities for employee volunteering and skill-based contributions

- Tax Benefits: Eligible for full CSR expenditure as per Companies Act provisions

- Stakeholder Value: Demonstrable commitment to rural development and inclusive growth

- Long-term Legacy: Creating sustainable community infrastructure with lasting impact

# 4. DETAILED PROJECT DESCRIPTION

## 4.1 Project Objectives

Primary Objective:

To empower rural communities in Mulugu or Jangaon districts by establishing Integrated Learning Centers that provide comprehensive access to education, digital literacy, healthcare, skill development, women's empowerment, and community services, thereby improving quality of life and creating pathways to sustainable livelihoods.

Specific Objectives:

- Establish 5 fully-functional Integrated Learning Centers in selected villages across Mulugu or Jangaon districts

- Provide 50,000+ rural residents with access to library resources, digital learning platforms, and knowledge repositories

- Train 25,000+ individuals in digital literacy and basic computer skills

- Skill 10,000+ youth in employable vocational skills and career development

- Economically empower 5,000+ women through entrepreneurship training and microenterprise support

- Improve health and wellness outcomes for 15,000+ individuals through fitness programs and health awareness

- Support 3,000+ farmers with modern agricultural training and market linkages

- Preserve and promote local cultural heritage through dedicated arts and cultural programs

- Create sustainable, community-managed development models replicable across rural India

## 4.2 Project Components and Facilities

### Component 1: Integrated Library System

Objective: Provide comprehensive access to knowledge resources, promoting reading culture and supporting academic excellence.

Infrastructure:

- Physical library space: 500-800 sq ft with comfortable seating for 25-30 readers

- Book collection: 3,000-5,000 books covering academic, competitive exam, fiction, non-fiction, and regional literature

- Reading room with study tables, chairs, and adequate lighting

- Cataloging system (digital or manual) for easy book management

- Newspaper and magazine section with daily subscriptions

- Employment news bulletins and government circulars

Target Beneficiaries:

- Students (Classes 6-12 and higher education)

- Competitive exam aspirants

- Adult learners and lifelong learning enthusiasts

- Researchers and academicians

Expected Outcomes:

- 10,000+ library members per ILC

- 15,000+ book issues annually per center

- Improved academic performance and competitive exam success rates

- Enhanced reading culture and knowledge awareness

### Component 2: Digital Kiosk Lab and e-Learning Center

Objective: Bridge the digital divide by providing internet access, digital literacy training, and e-governance services.

Infrastructure:

- 10 internet-enabled computers/laptops with latest configurations

- High-speed internet connectivity (minimum 100 Mbps)

- Printers, scanners, and photocopying machines

- Digital kiosks for e-governance access

- Dedicated e-learning software and platforms

- Audio-visual equipment for webinar participation

Services Offered:

- Basic computer training and digital literacy courses

- Access to online educational resources and MOOCs

- E-governance services (birth/death certificates, ration cards, land records)

- Online job applications and employment portals

- Email account creation and management

- Digital payment and banking services

- Government scheme information and application support

Expected Outcomes:

- 5,000+ individuals trained in digital literacy per ILC

- 80% digital literacy rate among target population

- Improved access to government services and schemes

- Enhanced employment opportunities through online platforms

### Component 3: Health and Fitness Facilities

Objective: Promote physical and mental wellness through fitness programs, health awareness, and preventive healthcare services.

Infrastructure:

- Indoor gym: 400-600 sq ft with equipment for 10-15 users

- Gym equipment: Treadmills, exercise cycles, weights, resistance bands, yoga mats

- Outdoor sports facilities: Volleyball court, badminton courts, cricket practice area

- Children's play area with safe equipment

- Basic first-aid station and health monitoring equipment

- Yoga and meditation space

Programs and Services:

- Regular fitness training sessions and workout programs

- Yoga and meditation classes

- Quarterly health check-up camps (BP, diabetes, BMI screening)

- Health awareness workshops on nutrition, hygiene, disease prevention

- Sports tournaments and competitions

- Mental health awareness and counseling support

Expected Outcomes:

- 3,000+ regular fitness facility users per ILC

- 5,000+ participants in health awareness programs annually

- 2,000+ individuals screened in health camps per year

- Measurable improvements in community health indicators

### Component 4: Women Empowerment Centers

Objective: Enable women's economic independence through skill development, entrepreneurship training, and microenterprise support.

Infrastructure:

- Dedicated workspace: 300-500 sq ft for small-scale industries

- Industrial sewing machines (5-10 units)

- Equipment for paper/leaf plate manufacturing

- Sanitary napkin production machinery

- Tools and materials for handicrafts and traditional crafts

- Training hall for capacity building programs

Services and Training:

- SHG formation and management training

- Tailoring and garment manufacturing skills

- Handicraft and artisan product development

- Food processing and packaging

- Financial literacy and bookkeeping

- Digital marketing and e-commerce

- Product quality control and branding

- Market linkage facilitation

Expected Outcomes:

- 1,000+ women enrolled in empowerment programs per ILC

- 50+ SHGs formed and functioning

- 30-40 microenterprises established per center

- Average 40-60% increase in household income for participants

- Enhanced women's decision-making and leadership roles

# 5. IMPLEMENTATION STRATEGY AND TIMELINE

## 5.1 Project Implementation Phases

### Phase 1: Planning and Preparation (Months 1-6)

- Finalize village selection through needs assessment and community consultations

- Secure land through government allocation, community donation, or lease

- Complete detailed architectural designs and civil engineering plans

- Obtain necessary approvals and clearances

- Finalize CSR partnership agreements and funding disbursement schedule

- Recruit core project team and field staff

- Establish project governance structures and committees

- Develop operational manuals, SOPs, and training curricula

- Initiate community mobilization and awareness campaigns

### Phase 2: Infrastructure Development (Months 7-18)

- Construction of ILC buildings (2,500-3,500 sq ft per center)

- Installation of electrical, plumbing, and internet infrastructure

- Procurement of furniture, equipment, and learning materials

- Library setup with book acquisition and cataloging

- Digital lab setup with computers and networking

- Gym and sports facility establishment

- Women's center equipment installation

- Safety and security systems installation

- Quality checks and facility testing

### Phase 3: Capacity Building and Soft Launch (Months 19-24)

- Staff recruitment and intensive training

- Volunteer identification and orientation

- Formation of management committees and user groups

- Pilot testing of all facilities with limited users

- Development of digital platforms and MIS

- Baseline data collection for impact assessment

- Community orientation and membership drives

- Soft launch with phased service rollout

### Phase 4: Full Operations and Scaling (Months 25-36)

- Grand inauguration and official launch of all ILCs

- Full-scale operations across all components

- Regular program delivery and service provision

- Continuous monitoring and mid-term evaluation

- Community ownership transition activities

- Knowledge documentation and learning dissemination

- End-term impact assessment and reporting

- Sustainability planning and exit strategy development

## 5.2 Detailed Activity Timeline (Gantt Chart)

| Activity | Start Month | End Month | Duration | Responsibility |
| --- | --- | --- | --- | --- |
| Village Selection & Site Finalization | 1 | 3 | 3 months | Project Director |
| Architectural Design & Approvals | 2 | 5 | 4 months | Engineering Team |
| Building Construction | 7 | 16 | 10 months | Construction Team |
| Equipment Procurement & Installation | 14 | 18 | 5 months | Procurement Team |
| Staff Recruitment & Training | 17 | 22 | 6 months | HR Team |
| Community Mobilization | 4 | 36 | 33 months | Field Team |
| Pilot Testing & Soft Launch | 20 | 24 | 5 months | Operations Team |
| Full Operations & Service Delivery | 25 | 36 | 12 months | All Teams |
| Monitoring & Evaluation | 1 | 36 | 36 months | M&E Team |

# 6. DETAILED PROJECT BUDGET

## 6.1 Capital Expenditure (CAPEX) - Per ILC Center

| S.No | Budget Head | Quantity | Unit Cost (₹) | Total Cost (₹) |
| --- | --- | --- | --- | --- |
| A. | LAND & BUILDING |  |  |  |
| 1 | Land Acquisition/Lease (Community Contributed) | 1 Acre | Variable | In-kind |
| 2 | Building Construction (3000 sq ft) | 3000 sq ft | 800-1000 | 25,00,000 |
| 3 | Electrical & Plumbing Works | Lump Sum | - | 3,50,000 |
| 4 | Internet & IT Infrastructure | Lump Sum | - | 2,00,000 |
| B. | LIBRARY SETUP |  |  |  |
| 5 | Books (Academic, Fiction, Reference) | 3500 books | 300-500 | 14,00,000 |
| 6 | Library Furniture (Racks, Tables, Chairs) | Lump Sum | - | 3,00,000 |
| C. | DIGITAL KIOSK LAB |  |  |  |
| 7 | Desktop Computers/Laptops | 10 units | 40,000 | 4,00,000 |
| 8 | Printer, Scanner & Peripherals | Lump Sum | - | 1,50,000 |
| 9 | Computer Tables & Chairs | 10 sets | 8,000 | 80,000 |
| D. | HEALTH & FITNESS |  |  |  |
| 10 | Gym Equipment (Treadmill, Cycles, Weights) | Lump Sum | - | 3,00,000 |
| 11 | Outdoor Sports Facilities & Equipment | Lump Sum | - | 4,00,000 |
| E. | WOMEN EMPOWERMENT CENTER |  |  |  |
| 12 | Sewing Machines & Tools | 8 units | 25,000 | 2,00,000 |
| 13 | Other Production Equipment | Lump Sum | - | 1,50,000 |
| F. | MISCELLANEOUS |  |  |  |
| 14 | Training Hall Furniture & AV Equipment | Lump Sum | - | 2,50,000 |
| 15 | Safety, Security & Signage | Lump Sum | - | 1,50,000 |
|  | TOTAL CAPITAL EXPENDITURE (Per ILC) |  |  | ₹ 68,30,000 |

# CONCLUSION AND CALL TO ACTION

The Integrated Learning Centers (ILCs) project represents a transformative opportunity to create lasting impact in rural Telangana through comprehensive, sustainable, and community-driven development. This CSR partnership offers corporate partners the ability to address multiple Schedule VII objectives through a single integrated intervention, demonstrating measurable social impact while building strong community relationships.

With a total project outlay of ₹4.35 crore for 5 centers, this investment will directly benefit 50,000+ individuals and indirectly impact 1,00,000+ lives across education, health, livelihoods, and social empowerment. The project's robust implementation framework, experienced implementing organization, and comprehensive monitoring mechanisms ensure accountability, transparency, and optimal utilization of CSR funds.

We invite your esteemed organization to partner with Give For Society in this transformative rural development initiative. Together, we can empower communities, create opportunities, and build a more inclusive and prosperous India.

For further details, site visits, or partnership discussions, please contact:

Give For Society

Hyderabad, Telangana, India

***