# Rural Youth Digital Employability & Future Skills Initiative

## (Data Science, AI & Workforce Readiness Programme)

### For Mining-Affected Rural & Tribal Communities

### Jayashankar Bhupalpally District, Telangana

### Under District Mineral Foundation Trust (DMFT) / PMKKKY

Presented as: # MP Initiative under DMFT

Implementation Support: Give For Society

Technical & Training Ecosystem Support: Industry & Digital Learning Partners

# SECTION 11 — DETAILED BUDGET FRAMEWORK

## Semi-DPR Financial Structure

The proposed Rural Youth Digital Employability & Future Skills Initiative is designed as a district-level workforce readiness and digital employability programme under the District Mineral Foundation Trust (DMFT) / PMKKKY framework.

The budget framework has been prepared based on:

- rural youth employability enhancement,

- digital literacy systems,

- AI/Data Science awareness,

- workforce readiness programmes,

- GVK-based skilling delivery,

- and hybrid digital learning ecosystems.

The proposed financial structure emphasizes: # Low-Cost Convergence-Based Skill Development through utilization of existing Grama Vikas Kendra (GVK) infrastructure and shared digital learning assets.

# FROZEN PHASE-1 IMPLEMENTATION MODEL

| Parameter | Approved Assumption |
| --- | --- |
| Coverage Model | Pilot + Expansion |
| Training Infrastructure | Existing GVK Ecosystem |
| Delivery Model | Hub-and-Spoke |
| Programme Duration | 2 Years |
| Training Duration per Cohort | 3 Months |
| Total Beneficiaries | 1000 Youth |
| Target Groups | Rural, Tribal, Women & Unemployed Youth |
| Delivery Mode | Hybrid |
| Certification Model | Industry-Aligned |
| Computer Infrastructure | Shared GVK Systems |
| Budget Strategy | Low-Cost Operational Delivery Model |

# SECTION A — LMS, CURRICULUM & DIGITAL LEARNING SYSTEMS

## Scope

Development and deployment of: # Hybrid Digital Learning Ecosystem

supporting:

- digital literacy,

- data analytics awareness,

- AI/ML fundamentals,

- employability skills,

- and structured online learning.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| LMS Licensing & Platform Access | Lump Sum | — | ₹12,00,000 |
| Digital Curriculum Development | Lump Sum | — | ₹10,00,000 |
| Learning Content & Assessments | Lump Sum | — | ₹8,00,000 |
| Cloud & Digital Learning Tools | Lump Sum | — | ₹5,00,000 |
| Student Digital Access Support | Lump Sum | — | ₹5,00,000 |

### Subtotal

# ₹40,00,000

# SECTION B — TRAINING DELIVERY & TECHNICAL SESSIONS

## Scope

Delivery of: # Structured Technical Training Programmes

covering:

- digital literacy,

- Python basics,

- SQL,

- Excel,

- Power BI,

- AI/ML awareness,

- employability readiness,

- and digital productivity tools.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Master Trainers | 24 Months | ₹60,000/month | ₹14,40,000 |
| Visiting Industry Trainers | Lump Sum | — | ₹10,00,000 |
| Live Technical Sessions | Lump Sum | — | ₹8,00,000 |
| Workshop & Bootcamp Sessions | Lump Sum | — | ₹7,00,000 |
| Student Learning Materials | Lump Sum | — | ₹5,00,000 |

### Subtotal

# ₹44,40,000

# SECTION C — GVK-BASED TRAINING OPERATIONS

## Scope

Operational support for:

- GVK-based learning delivery,

- scheduling,

- digital lab utilization,

- and local training coordination.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| GVK Training Coordination Support | 5 Centers | ₹3,00,000 | ₹15,00,000 |
| Utility & Operational Support | Lump Sum | — | ₹5,00,000 |
| Training Lab Maintenance Support | Lump Sum | — | ₹5,00,000 |
| Local Mobilization & Registration | Lump Sum | — | ₹5,00,000 |

### Subtotal

# ₹30,00,000

# SECTION D — EMPLOYABILITY & CAREER READINESS SYSTEMS

## Scope

Career readiness systems supporting:

- resume preparation,

- interview readiness,

- employer engagement,

- and workforce transition support.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Resume & Interview Workshops | Lump Sum | — | ₹5,00,000 |
| Placement Preparation Sessions | Lump Sum | — | ₹5,00,000 |
| Employer Connect & Career Events | Lump Sum | — | ₹6,00,000 |
| Soft Skills & Communication Training | Lump Sum | — | ₹5,00,000 |

### Subtotal

# ₹21,00,000

# SECTION E — CERTIFICATION & ASSESSMENT SYSTEMS

## Scope

Evaluation, assessment, certification, and capstone review systems.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Online Assessments & Evaluations | Lump Sum | — | ₹4,00,000 |
| Certification Systems | Lump Sum | — | ₹5,00,000 |
| Capstone Evaluation Support | Lump Sum | — | ₹4,00,000 |
| Student Performance Analytics | Lump Sum | — | ₹3,00,000 |

### Subtotal

# ₹16,00,000

# SECTION F — OUTREACH, COMMUNITY MOBILIZATION & WOMEN PARTICIPATION

## Scope

Programme outreach and beneficiary mobilization focused on:

- rural youth,

- tribal communities,

- women participation,

- and first-generation learners.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| Community Outreach Campaigns | Lump Sum | — | ₹5,00,000 |
| Women Participation Mobilization | Lump Sum | — | ₹4,00,000 |
| Awareness Materials & IEC | Lump Sum | — | ₹3,00,000 |
| Registration & Enrollment Support | Lump Sum | — | ₹3,00,000 |

### Subtotal

# ₹15,00,000

# SECTION G — MONITORING, MIS & IMPACT TRACKING

## Scope

Programme tracking systems including:

- attendance monitoring,

- student progression,

- assessments,

- placement tracking,

- and dashboard reporting.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| MIS & Dashboard Systems | Lump Sum | — | ₹6,00,000 |
| Data Collection & Analytics | Lump Sum | — | ₹4,00,000 |
| Monitoring & Evaluation | Lump Sum | — | ₹5,00,000 |
| Reporting & Documentation | Lump Sum | — | ₹4,00,000 |

### Subtotal

# ₹19,00,000

# SECTION H — PROGRAMME MANAGEMENT & ADMINISTRATIVE SUPPORT

## Scope

Programme management, district coordination, technical administration, and operational oversight.

## Budget Components

| Component | Qty | Unit Cost | Total |
| --- | --- | --- | --- |
| District Programme Manager | 24 Months | ₹60,000/month | ₹14,40,000 |
| Technical Programme Coordinator | 24 Months | ₹40,000/month | ₹9,60,000 |
| Administrative Support | Lump Sum | — | ₹5,00,000 |
| Travel & Coordination Support | Lump Sum | — | ₹5,00,000 |

### Subtotal

# ₹34,00,000

# SECTION I — CONTINGENCY RESERVE

| Component | Total |
| --- | --- |
| Contingency Reserve | ₹10,00,000 |

# PHASE-1 CONSOLIDATED BUDGET SUMMARY

| Component | Total |
| --- | --- |
| LMS & Digital Learning Systems | ₹40,00,000 |
| Training Delivery & Technical Sessions | ₹44,40,000 |
| GVK-Based Training Operations | ₹30,00,000 |
| Employability & Career Readiness | ₹21,00,000 |
| Certification & Assessment Systems | ₹16,00,000 |
| Outreach & Women Participation | ₹15,00,000 |
| Monitoring & MIS | ₹19,00,000 |
| Programme Management & Administration | ₹34,00,000 |
| Contingency Reserve | ₹10,00,000 |

# TOTAL ESTIMATED PHASE-1 BUDGET

# ₹2,29,40,000

## (₹2.29 Crores)

# COST POSITIONING UNDER DMFT

The proposed financial structure has been designed as: # Convergence-Based Rural Workforce Readiness Infrastructure

focused on:

- employability,

- digital literacy,

- workforce transition,

- women participation,

- and future-ready digital skills.

This approach ensures:

- low infrastructure duplication,

- shared public asset utilization,

- scalability,

- and long-term livelihood impact.

# COST EFFICIENCY INDICATORS

| Indicator | Estimate |
| --- | --- |
| Cost per Student | ~₹23,000 |
| Direct Beneficiaries | 1000 Youth |
| GVK Training Hubs | 5 |
| Training Duration per Cohort | 3 Months |
| Programme Duration | 2 Years |

# IMPLEMENTATION PHASE STRUCTURE

| Phase | Timeline |
| --- | --- |
| Phase 1 | Outreach & enrollment |
| Phase 2 | LMS activation & onboarding |
| Phase 3 | Technical training delivery |
| Phase 4 | Assessments & capstone projects |
| Phase 5 | Placement & employability support |
| Phase 6 | Monitoring & reporting |

# PROPOSED EXPANSION MODEL

Following successful Phase-1 implementation:

- advanced skilling tracks,

- entrepreneurship incubation,

- women-focused digital programmes,

- and district-wide digital employability ecosystems

may be considered under future DMFT phases.

# FINANCIAL SUSTAINABILITY APPROACH

The initiative emphasizes:

- shared public infrastructure,

- hybrid digital delivery,

- convergence-based operations,

- and scalable workforce readiness systems.

This strengthens: # long-term sustainability and rural digital employability ecosystems across mining-affected rural and tribal communities.