STANDARD DETAILED PROJECT REPORT (DPR) TEMPLATE

For DMFT / PMKKKY District Development Proposals

«PROJECT NAME»

«Subtitle / Thematic Description»

Jayashankar Bhupalpally District, Telangana

Under District Mineral Foundation Trust (DMFT) / PMKKKY

| Particulars | Details |
| --- | --- |
| Presented as | MP Initiative under DMFT |
| Implementation Support | Give For Society |
| Submitted to | District Collector & DMFT Governing Council |
| District | Jayashankar Bhupalpally, Telangana |
| Submission Date | «DD / MM / YYYY» |
| Project Duration | «X years (Phase 1)» |
| Indicative Budget | ₹ «X.X Crores» |
| DPR Version | v1.0 |

# How to Use This Template

This document is the standard Detailed Project Report (DPR) structure to be used for all five flagship DMFT proposals under the Jayashankar Bhupalpally District Development Portfolio. Each of the five projects — Sthree Swabhiman, ArogyaSetu, Grama Vikas Kendras, Vidya Pragathi, and Kaushalya Pragathi — will be developed by populating this template with project-specific content.

### Reading the formatting

- Black regular text: standard headings and structural elements — keep as-is.

- «Text in chevrons» or [text in brackets]: placeholder content that must be replaced with project-specific information.

- Italic grey text: example content showing what kind of information goes in each section — replace with actual content.

- Cream-coloured Guidance Boxes: instructions for what to write in that section — these boxes can be deleted once the section is populated.

### Section status workflow

Each project DPR should track the status of each section as: (a) Not Started, (b) Drafted, (c) Reviewed, (d) Finalized. The Annexure 0 — Section Status Tracker at the end of this template can be copied to the front of each project DPR to maintain progress visibility.

### Critical sections that must not be skipped

- Section 10 — Detailed Budget with Unit Cost Justification (the single most reviewed section by DMFT).

- Section 12 — Monitoring Framework & KPI Matrix (required for DMFT release of tranches).

- Section 14 — Risk Assessment & Mitigation (frequently flagged as missing in NGO proposals).

- Section 15 — Institutional Convergence & Department Mapping (critical for MP-led DMFT proposals).

# Table of Contents

Cover Page

How to Use This Template

SECTION 1   — Executive Summary

SECTION 2   — District Context

SECTION 3   — Problem Statement

SECTION 4   — PMKKKY / DMFT Alignment

SECTION 5   — Project Objectives

SECTION 6   — Target Beneficiaries

SECTION 7   — Geographic Coverage

SECTION 8   — Project Components

SECTION 9   — Implementation Strategy & Timeline

SECTION 10 — Detailed Budget & Cost Justification

SECTION 11 — Procurement & Operational Model

SECTION 12 — Monitoring Framework & KPI Matrix

SECTION 13 — Sustainability Plan

SECTION 14 — Risk Assessment & Mitigation

SECTION 15 — Institutional Convergence & Department Mapping

SECTION 16 — About Give For Society

SECTION 17 — Annexures

Annexure 0 — Section Status Tracker

# SECTION 1 — Executive Summary

📌 GUIDANCE — Executive Summary • Length: 1 to 1.5 pages. The Collector and DMFT committee read this first and sometimes only this. • Lead with the problem in one sentence, then the proposed response, then expected outcomes. • Always state: total beneficiaries, total institutions/villages covered, total budget, duration, lead implementer. • End with PMKKKY priority sector alignment in one sentence.

## 1.1  Project Overview

«Open with a 3–4 sentence overview describing what the project is, who it serves, and why it is needed in mining-affected Jayashankar Bhupalpally district. State the project name, the lead presenter (MP under DMFT), and the implementation support partner (Give For Society).»

## 1.2  Project Snapshot

| Parameter | Details |
| --- | --- |
| Project Title | «Full project name» |
| Thematic Focus | «e.g. Adolescent dignity & WASH infrastructure» |
| Geographic Coverage | «Number of mandals, villages, institutions» |
| Direct Beneficiaries | «Number, with breakdown by category» |
| Indirect Beneficiaries | «Number» |
| Project Duration | «Phase 1 duration in years» |
| Total Phase-1 Budget | ₹ «X.XX Crores» |
| Funding Source | District Mineral Foundation Trust (DMFT) / PMKKKY |
| Lead Presenter | Member of Parliament, «Constituency» |
| Implementation Partner | Give For Society |
| PMKKKY Priority Sectors | «List the relevant priority areas, e.g. Health, Sanitation, Women & Child Welfare» |

## 1.3  Expected Impact in One Paragraph

«In 4–5 sentences, summarize what the district will look different after Phase 1 implementation — specifically, which gaps will be closed, which institutions will be strengthened, and what scalable model is being created. This is the closing pitch of the Executive Summary.»

# SECTION 2 — District Context

📌 GUIDANCE — District Context • Establish credibility by showing understanding of Jayashankar Bhupalpally as a mining-affected district. • Cite specifics: number of mandals, tribal habitations, residential institutions, mining influence zones. • Connect district characteristics directly to the gap your project addresses — do not write generic district description.

## 2.1  About Jayashankar Bhupalpally District

«Describe the district: rural and mining-affected character, tribal and forest-fringe communities, key mandals, and the social demographics relevant to this project. Keep it focused on what is relevant to the proposed intervention.»

## 2.2  Mining-Affected Profile & PMKKKY Relevance

«State briefly that the district is covered under PMKKKY due to its mining footprint, and explain why mining-affected communities specifically face the gaps that this project addresses.»

## 2.3  District Demographic Profile (Relevant to this Project)

| Parameter | Figure / Description |
| --- | --- |
| Total Population | [insert from census / district handbook] |
| Rural Population % | [insert] |
| Tribal Population % | [insert] |
| Number of Mandals | [insert] |
| Mining-Affected Mandals | [insert names] |
| Scheduled Areas in District | [insert] |
| Project-Relevant Sub-Demographic | [e.g. adolescent girls aged 11–18, rural youth aged 18–28, ZPHS enrollment] |

## 2.4  Existing Government Infrastructure (Relevant to this Project)

«List relevant existing infrastructure — KGBVs, ZPHS schools, PHCs, CHCs, anganwadis, residential welfare institutions — depending on project theme. State numbers wherever possible. This sets up the case for what is missing.»

# SECTION 3 — Problem Statement

📌 GUIDANCE — Problem Statement • Be specific and evidence-based. Use district data, government surveys, or visible infrastructure gaps. • Avoid generic statements. Tie each problem to either institutional failure, infrastructure gap, awareness gap, or accessibility barrier. • Frame problems in a way that maps cleanly to the project components later — this proves coherence.

## 3.1  Core Problem

«State the central problem in 2–3 sentences. What is the gap, who does it affect, and what is the consequence of inaction?»

## 3.2  Key Issues Identified

«Below are 5–8 bullet points naming the specific issues this project addresses. Each issue should later map to a project component in Section 8.»

- [Issue 1 — describe specifically, e.g. lack of safe menstrual waste disposal in 70+ residential institutions]

- [Issue 2]

- [Issue 3]

- [Issue 4]

- [Issue 5]

## 3.3  Vulnerable Groups Most Affected

| Group | Specific Vulnerability |
| --- | --- |
| [e.g. Adolescent tribal girls in residential schools] | [e.g. dependency on institutional sanitation throughout academic year] |
| [Group 2] | [Vulnerability] |
| [Group 3] | [Vulnerability] |
| [Group 4] | [Vulnerability] |

## 3.4  Consequences of Inaction

«State what happens if the problem is not addressed — measured in absenteeism, health outcomes, dropout rates, livelihood loss, etc. Make the case urgent.»

# SECTION 4 — PMKKKY / DMFT Alignment

📌 GUIDANCE — PMKKKY / DMFT Alignment • PMKKKY mandates 60% spend on High Priority Areas (HPAs). Always show which HPAs this project addresses. • Use the mapping table format below — DMFT committees scan this table to verify eligibility. • Also align with Telangana State DMFT priorities, Scheduled Area requirements, and SDGs.

## 4.1  PMKKKY High Priority Area Mapping

| PMKKKY Priority Area | How This Project Addresses It |
| --- | --- |
| Drinking Water Supply | [fill or write N/A] |
| Environment Preservation | [fill or write N/A] |
| Health Care | [fill or write N/A] |
| Education | [fill or write N/A] |
| Welfare of Women & Children | [fill or write N/A] |
| Welfare of Aged & Disabled | [fill or write N/A] |
| Skill Development | [fill or write N/A] |
| Sanitation | [fill or write N/A] |

## 4.2  PMKKKY Other Priority Areas Addressed

| Other Priority Area | How This Project Addresses It |
| --- | --- |
| Physical Infrastructure | [fill or write N/A] |
| Irrigation | [fill or write N/A] |
| Energy & Watershed Development | [fill or write N/A] |
| Any other measure for environmental, economic & social well-being | [fill] |

## 4.3  Alignment with Telangana State DMFT Priorities

«Briefly state how the project aligns with Telangana-specific DMFT priorities for tribal welfare, residential institution support, rural healthcare, etc.»

## 4.4  Alignment with Scheduled Area / Tribal Welfare Priorities

«If applicable, describe how the project serves Scheduled Areas, ST communities, and tribal welfare institutions.»

## 4.5  Alignment with National Schemes & Convergence

| National Scheme | Convergence Linkage |
| --- | --- |
| Swachh Bharat Mission | [describe linkage or N/A] |
| Beti Bachao Beti Padhao | [describe linkage or N/A] |
| Ayushman Bharat | [describe linkage or N/A] |
| Samagra Shiksha / NEP 2020 | [describe linkage or N/A] |
| Skill India / PMKVY | [describe linkage or N/A] |
| Jal Jeevan Mission | [describe linkage or N/A] |
| National Health Mission | [describe linkage or N/A] |

## 4.6  Sustainable Development Goal (SDG) Alignment

| SDG | Contribution |
| --- | --- |
| SDG 3 — Good Health & Well-being | [describe or N/A] |
| SDG 4 — Quality Education | [describe or N/A] |
| SDG 5 — Gender Equality | [describe or N/A] |
| SDG 6 — Clean Water & Sanitation | [describe or N/A] |
| SDG 8 — Decent Work & Economic Growth | [describe or N/A] |
| SDG 10 — Reduced Inequalities | [describe or N/A] |

# SECTION 5 — Project Objectives

📌 GUIDANCE — Project Objectives • Objectives should be SMART: Specific, Measurable, Achievable, Relevant, Time-bound. • Each Primary Objective should later have at least one corresponding Project Component (Section 8) and one KPI (Section 12). • Keep to 5–6 Primary Objectives. More than that signals an unfocused proposal.

## 5.1  Primary Objectives

«List 5–6 primary objectives. For each, give a 1-sentence statement followed by 2–3 bullet sub-points specifying scope.»

### Objective 1: [Name]

«1-sentence objective statement.»

- [Sub-point 1]

- [Sub-point 2]

### Objective 2: [Name]

«…»

### Objective 3: [Name]

«…»

### Objective 4: [Name]

«…»

### Objective 5: [Name]

«…»

## 5.2  Secondary Objectives

- [Secondary objective 1]

- [Secondary objective 2]

- [Secondary objective 3]

## 5.3  Long-Term Vision

«2–3 sentence statement of the long-term district-level vision this project contributes toward, beyond the immediate phase.»

# SECTION 6 — Target Beneficiaries

📌 GUIDANCE — Target Beneficiaries • Distinguish clearly between Direct (receive intervention directly) and Indirect (benefit downstream) beneficiaries. • Give numbers — not vague descriptions. DMFT committees compute cost-per-beneficiary from this section. • Show prioritization logic: why these groups, why now, why in this district.

## 6.1  Primary (Direct) Beneficiaries

| Beneficiary Category | Estimated Number | Selection Basis |
| --- | --- | --- |
| [Group 1, e.g. Adolescent girls in residential institutions] | [Number] | [e.g. residential dependency, institutional sanitation gap] |
| [Group 2] | [Number] | [Basis] |
| [Group 3] | [Number] | [Basis] |
| [Group 4] | [Number] | [Basis] |

## 6.2  Secondary (Indirect) Beneficiaries

| Stakeholder Group | Estimated Number | Role / Benefit |
| --- | --- | --- |
| [e.g. Teachers, wardens] | [Number] | [Capacity building & system continuity] |
| [Group 2] | [Number] | [Role] |
| [Group 3] | [Number] | [Role] |

## 6.3  Community-Level Indirect Reach

«Describe wider community impact: families of beneficiaries, surrounding villages, district-level ecosystems. Estimate a total indirect reach figure.»

## 6.4  Beneficiary Selection Criteria

- [Criterion 1 — e.g. priority to Scheduled Tribe / Scheduled Caste communities]

- [Criterion 2 — e.g. mining-affected mandal residency]

- [Criterion 3 — e.g. residential institution dependency]

- [Criterion 4]

## 6.5  Beneficiary Summary

| Beneficiary Type | Estimated Total |
| --- | --- |
| Direct Beneficiaries | [insert total] |
| Indirect Beneficiaries | [insert total] |
| Institutions Covered | [insert total] |
| Villages / Mandals Covered | [insert total] |

# SECTION 7 — Geographic Coverage

📌 GUIDANCE — Geographic Coverage • List the specific mandals and the rationale for choosing them. • Phase 1 / Phase 2 split: shows DMFT committee a realistic, scalable approach (avoid claiming district-wide rollout in Phase 1). • Mention coordination with district administration on mandal selection.

## 7.1  Proposed District Coverage

«1–2 paragraphs describing the geographic scope: full-district vs phase-wise rollout, mining-affected priority, tribal area focus.»

## 7.2  Phase-1 Priority Mandals

| Mandal | Project-Specific Focus | Estimated Coverage |
| --- | --- | --- |
| Bhupalpally | [focus] | [e.g. 5 institutions] |
| Kataram | [focus] | [coverage] |
| Mahadevpur | [focus] | [coverage] |
| Mutharam | [focus] | [coverage] |
| Palimela | [focus] | [coverage] |
| Chityal | [focus] | [coverage] |
| Tekumatla | [focus] | [coverage] |
| Regonda | [focus] | [coverage] |
| Mogullapalle | [focus] | [coverage] |

## 7.3  Phase-1 vs Phase-2 Coverage Strategy

| Phase | Coverage | Rationale |
| --- | --- | --- |
| Phase 1 | [e.g. 25 priority institutions across X mandals] | [Highest-vulnerability subset; pilot model before scaling] |
| Phase 2 | [Remaining institutions / mandals] | [Scaled rollout after Phase 1 learnings] |

## 7.4  Selection Criteria for Phase-1 Sites

- [Criterion 1 — e.g. mining influence intensity]

- [Criterion 2 — e.g. tribal / Scheduled Area presence]

- [Criterion 3 — e.g. existing infrastructure gap severity]

- [Criterion 4 — e.g. institutional concentration of target beneficiaries]

# SECTION 8 — Project Components

📌 GUIDANCE — Project Components • Each Component must map to one or more Objectives (Section 5) and have a corresponding Budget Head (Section 10). • Limit to 5–7 Components. Each Component = 1 page of detail. • For each Component: state activities, deliverables, target quantity, and the institutional pathway through which it will be delivered.

## 8.1  Component Overview

| # | Component Name | Brief Description |
| --- | --- | --- |
| 1 | [Component 1] | [1-line description] |
| 2 | [Component 2] | [1-line description] |
| 3 | [Component 3] | [1-line description] |
| 4 | [Component 4] | [1-line description] |
| 5 | [Component 5] | [1-line description] |

## 8.1.  Component 1: [Name]

### Description

«2–3 paragraphs explaining what this component does, who it serves, and how it integrates with the other components.»

### Activities

- [Activity 1]

- [Activity 2]

- [Activity 3]

### Deliverables & Quantities

| Deliverable | Quantity |
| --- | --- |
| [Deliverable 1] | [Number] |
| [Deliverable 2] | [Number] |

## 8.2.  Component 2: [Name]

### Description

«2–3 paragraphs explaining what this component does, who it serves, and how it integrates with the other components.»

### Activities

- [Activity 1]

- [Activity 2]

- [Activity 3]

### Deliverables & Quantities

| Deliverable | Quantity |
| --- | --- |
| [Deliverable 1] | [Number] |
| [Deliverable 2] | [Number] |

## 8.3.  Component 3: [Name]

### Description

«2–3 paragraphs explaining what this component does, who it serves, and how it integrates with the other components.»

### Activities

- [Activity 1]

- [Activity 2]

- [Activity 3]

### Deliverables & Quantities

| Deliverable | Quantity |
| --- | --- |
| [Deliverable 1] | [Number] |
| [Deliverable 2] | [Number] |

## 8.4.  Component 4: [Name]

### Description

«2–3 paragraphs explaining what this component does, who it serves, and how it integrates with the other components.»

### Activities

- [Activity 1]

- [Activity 2]

- [Activity 3]

### Deliverables & Quantities

| Deliverable | Quantity |
| --- | --- |
| [Deliverable 1] | [Number] |
| [Deliverable 2] | [Number] |

## 8.5.  Component 5: [Name]

### Description

«2–3 paragraphs explaining what this component does, who it serves, and how it integrates with the other components.»

### Activities

- [Activity 1]

- [Activity 2]

- [Activity 3]

### Deliverables & Quantities

| Deliverable | Quantity |
| --- | --- |
| [Deliverable 1] | [Number] |
| [Deliverable 2] | [Number] |

# SECTION 9 — Implementation Strategy & Timeline

📌 GUIDANCE — Implementation Strategy & Timeline • Use phased implementation — never a flat 'we will do everything in parallel' plan. • Standard pattern: Baseline → Procurement & Setup → Pilot → Scale-up → Monitoring → Sustainability. • Provide a Gantt-style table showing months on the X-axis. DMFT committees prefer visual timelines.

## 9.1  Implementation Approach

«1 paragraph stating the overall implementation philosophy — phased, convergence-based, institutionally embedded, etc.»

## 9.2  Phase-Wise Implementation Plan

### Phase 1: Baseline Assessment & Institutional Mapping (Months 1–2)

- [Key activity 1]

- [Key activity 2]

- [Deliverable / output]

### Phase 2: Procurement & Infrastructure Setup (Months 2–5)

- [Key activity 1]

- [Key activity 2]

- [Deliverable / output]

### Phase 3: Roll-Out & Activity Delivery (Months 4–10)

- [Key activity 1]

- [Key activity 2]

- [Deliverable / output]

### Phase 4: Capacity Building & Institutional Embedding (Months 6–11)

- [Key activity 1]

- [Key activity 2]

### Phase 5: Monitoring, Documentation & Phase-1 Review (Months 10–12)

- [Key activity 1]

- [Key activity 2]

## 9.3  Indicative Timeline (12-Month View)

| Activity Stream | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Baseline & Mapping | ● | ● | ○ |  |  |  |  |  |  |  |  |  |
| Procurement & Setup |  | ● | ● | ● | ● | ○ |  |  |  |  |  |  |
| Activity Delivery |  |  |  | ● | ● | ● | ● | ● | ● | ● | ○ |  |
| Capacity Building |  |  |  |  |  | ● | ● | ● | ● | ● | ● | ○ |
| Monitoring & Reporting |  |  | ○ |  | ○ |  | ○ |  | ○ |  | ● | ● |

Legend:  ● = Active month,  ○ = Planning / Review milestone

# SECTION 10 — Detailed Budget & Cost Justification

📌 GUIDANCE — Detailed Budget — most reviewed section • This is the single most-scrutinized section by DMFT. Every line item needs: Quantity × Unit Cost = Total. • Never present a budget as a range (e.g. ₹40–60 lakhs). Use a single number with justification. • Group expenses by Component (matching Section 8). Within each Component, list each line item. • Always include three sub-tables: A) Capital Expenditure (CAPEX), B) Operational Expenditure (OPEX), C) Programme Expenditure (PROGEX). • Add a Cost Justification narrative below the budget table — explain unit cost basis (market rate, govt rate, vendor quotes). • End with a Procurement Compliance note referencing GFR 2017 / Telangana procurement rules.

## 10.1  Budget Summary

| Budget Head | Phase-1 (₹ Lakhs) | % of Total |
| --- | --- | --- |
| A. Capital Expenditure (CAPEX) — infrastructure & equipment | [insert] | [%] |
| B. Programme Expenditure (PROGEX) — activities & beneficiary delivery | [insert] | [%] |
| C. Operational Expenditure (OPEX) — staffing, coordination, monitoring | [insert] | [%] |
| D. Contingency (≤ 5%) | [insert] | [%] |
| TOTAL PHASE-1 BUDGET | [insert] | 100% |

## 10.2  Detailed Component-Wise Budget

### Component 1: [Name]

| Item | Unit | Qty | Unit Cost (₹) | Total (₹) |
| --- | --- | --- | --- | --- |
| [Item 1] | [unit] | [qty] | [cost] | [total] |
| [Item 2] | [unit] | [qty] | [cost] | [total] |
| Sub-total Component 1 |  |  |  | [total] |

### Component 2: [Name]

| Item | Unit | Qty | Unit Cost (₹) | Total (₹) |
| --- | --- | --- | --- | --- |
| [Item 1] | [unit] | [qty] | [cost] | [total] |
| [Item 2] | [unit] | [qty] | [cost] | [total] |
| Sub-total Component 2 |  |  |  | [total] |

### Component 3: [Name]

| Item | Unit | Qty | Unit Cost (₹) | Total (₹) |
| --- | --- | --- | --- | --- |
| [Item 1] | [unit] | [qty] | [cost] | [total] |
| Sub-total Component 3 |  |  |  | [total] |

(Repeat sub-tables for Components 4 and 5 as needed.)

## 10.3  Operational & Monitoring Budget

| Head | Annual Cost (₹) | Total Phase-1 (₹) |
| --- | --- | --- |
| Programme Manager | [cost] | [total] |
| Field Coordinators | [cost] | [total] |
| M&E Officer | [cost] | [total] |
| Travel & field logistics | [cost] | [total] |
| Office, communication, reporting | [cost] | [total] |
| External evaluation / audit | [cost] | [total] |
| Sub-total OPEX |  | [total] |

## 10.4  Cost Justification Narrative

«For each major line item costing above ₹2 lakhs, provide a brief justification: (i) basis of unit cost (vendor quote / market rate / govt rate), (ii) why the quantity was chosen, (iii) any cost-comparison with similar implementations elsewhere. This narrative is what DMFT technical evaluators read.»

## 10.5  Procurement Compliance

- All procurement will follow General Financial Rules (GFR) 2017 norms.

- Tenders above prescribed thresholds will be routed via Telangana State e-procurement portal / GeM where applicable.

- Three competitive quotations will be obtained for procurements between [₹X lakh] and [₹Y lakh].

- Single-source procurement (if any) will be supported by documented justification and DMFT approval.

## 10.6  Funding Pattern

| Source | Contribution (₹ Lakhs) | % Share |
| --- | --- | --- |
| DMFT / PMKKKY Grant | [amount] | [%] |
| Convergence (other depts) | [amount] | [%] |
| CSR / Private Co-Funding (if any) | [amount] | [%] |
| Give For Society (in-kind / leveraged) | [amount] | [%] |
| TOTAL | [total] | 100% |

# SECTION 11 — Procurement & Operational Model

📌 GUIDANCE — Procurement & Operational Model • Specify who procures what, through which channel, and to which technical standard. • For infrastructure items, name the BIS / ISI / ISO standards that procurement will conform to. • Define the operational chain: District Collector → DMFT Cell → Implementation Partner → On-Ground Team.

## 11.1  Procurement Plan

| Category | Items | Procurement Channel | Technical Standard |
| --- | --- | --- | --- |
| Infrastructure / equipment | [list] | [GeM / e-procurement / tender] | [BIS / ISI / ISO ref] |
| Consumables / supplies | [list] | [3-quote / GeM] | [Standard] |
| Services / training | [list] | [empanelment / tender] | [Standard] |
| IT & digital systems | [list] | [GeM / vendor empanelment] | [Standard] |

## 11.2  Operational Chain of Implementation

- District Collector (DMFT Chairperson): overall sanction & oversight.

- DMFT Cell / Member Secretary: tranche releases, compliance review, reporting.

- Line Department (e.g. Education / Health / Welfare / Rural Dev): technical clearance & convergence facilitation.

- Give For Society (Implementation Partner): field execution, beneficiary engagement, documentation, monitoring.

- Institutional Focal Persons (e.g. school HMs, PHC MOs, sarpanches): site-level continuity.

## 11.3  Staffing Plan

| Role | Number | Reporting To | Key Responsibility |
| --- | --- | --- | --- |
| Programme Manager | 1 | Project Director | Overall delivery, DMFT liaison |
| District Coordinator | [N] | Programme Manager | District-level coordination |
| Field Coordinators | [N] | District Coordinator | Mandal-level rollout |
| Trainers / Specialists | [N] | Programme Manager | Capacity building & content delivery |
| M&E Officer | 1 | Programme Manager | Monitoring, reporting, KPI tracking |
| Finance & Admin | 1 | Programme Manager | Procurement, accounts, audit |

# SECTION 12 — Monitoring Framework & KPI Matrix

📌 GUIDANCE — Monitoring Framework & KPI Matrix • DMFT releases tranches against monitoring milestones. A clear KPI matrix is non-negotiable. • Distinguish Output KPIs (what was delivered) from Outcome KPIs (what changed for beneficiaries). • Tag each KPI with: baseline (current), target (Phase-1 end), measurement method, frequency, responsible person.

## 12.1  Monitoring Approach

«1 paragraph stating the M&E philosophy: institutional baseline, mid-line tracking, end-line evaluation, plus monthly operational dashboards.»

## 12.2  Output KPI Matrix (Delivery Indicators)

| KPI | Baseline | Phase-1 Target | Measurement Method | Frequency |
| --- | --- | --- | --- | --- |
| [Output KPI 1, e.g. # institutions covered] | 0 | [N] | [institutional records] | Quarterly |
| [Output KPI 2] | [baseline] | [target] | [method] | [freq] |
| [Output KPI 3] | [baseline] | [target] | [method] | [freq] |
| [Output KPI 4] | [baseline] | [target] | [method] | [freq] |

## 12.3  Outcome KPI Matrix (Impact Indicators)

| KPI | Baseline | Phase-1 Target | Measurement Method | Frequency |
| --- | --- | --- | --- | --- |
| [Outcome KPI 1, e.g. % reduction in absenteeism] | [baseline %] | [target %] | [survey / records] | Annual |
| [Outcome KPI 2] | [baseline] | [target] | [method] | [freq] |
| [Outcome KPI 3] | [baseline] | [target] | [method] | [freq] |

## 12.4  Reporting Schedule

| Report Type | Frequency | Submitted To |
| --- | --- | --- |
| Operational Dashboard | Monthly | DMFT Cell + Implementation Partner |
| Progress Report | Quarterly | DMFT Governing Council |
| Financial Utilisation Report | Quarterly | DMFT Cell |
| Mid-Term Review | Month 6 | Collector + DMFT |
| End-of-Phase Evaluation | Month 12 | Collector + DMFT + MP Office |
| External Audit | Annual | DMFT Cell |

## 12.5  Third-Party Verification

«State the proposed third-party verification arrangement — e.g. independent NGO audit, academic institutional partner, or government empanelled evaluator. This strengthens credibility significantly.»

# SECTION 13 — Sustainability Plan

📌 GUIDANCE — Sustainability Plan • DMFT does not want one-off interventions. Show how the work continues after the grant period ends. • Cover all four dimensions: institutional, financial, operational, behavioural.

## 13.1  Sustainability Approach

«1 paragraph framing why this project is designed for continuity — not dependence.»

## 13.2  Institutional Sustainability

«How will the host institutions (schools, PHCs, village centres, etc.) own and operate the intervention after Phase 1? Specify focal-person designation, integration into institutional routines, and reporting hooks.»

## 13.3  Financial Sustainability

«How will recurring costs (maintenance, consumables, electricity, staff) be covered post-Phase-1? Options include: (a) integration into existing govt scheme budgets, (b) DMFT recurring allocation, (c) institutional/school maintenance fund, (d) CSR co-funding, (e) Phase-2 DMFT submission.»

## 13.4  Operational Sustainability

«SOPs, maintenance protocols, training-of-trainers cascade, AMC arrangements for equipment, and institutional handover plan.»

## 13.5  Behavioural Sustainability

«Awareness and ownership building so that beneficiary behaviour change persists — peer leaders, community champions, IEC reinforcement.»

## 13.6  Sustainability Matrix

| Dimension | Mechanism | Owner Post-Phase-1 |
| --- | --- | --- |
| Institutional | [mechanism] | [owner] |
| Financial | [mechanism] | [owner] |
| Operational | [mechanism] | [owner] |
| Behavioural | [mechanism] | [owner] |

# SECTION 14 — Risk Assessment & Mitigation

📌 GUIDANCE — Risk Assessment & Mitigation • Most NGO proposals skip this section. Including it visibly strengthens the proposal in committee review. • Cover at least: implementation, financial, institutional, technical, beneficiary, and external risks. • For each risk: Likelihood (L/M/H), Impact (L/M/H), Mitigation Strategy.

## 14.1  Risk Register

| Risk Category | Risk Description | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| Implementation | [Delay in mandal-level rollout] | M | M | [Phased rollout; pre-baseline mapping; weekly tracker] |
| Financial | [Tranche release delays from DMFT] | M | H | [Bridge corpus from GFS; cash-flow planning] |
| Institutional | [Staff transfers in line departments] | M | M | [MoU at institutional, not individual, level] |
| Technical | [Equipment failure or substandard supply] | L | H | [BIS/ISI compliance; vendor warranties; AMC] |
| Beneficiary | [Low community uptake / participation] | L | M | [ASHA & sarpanch engagement; pre-launch IEC] |
| External | [Weather / unrest / political shifts] | L | M | [Quarterly contingency review; risk reserve] |
| Procurement | [Tender failure or single-bidder] | L | M | [Vendor empanelment; alt-procurement routes] |
| Reputational | [Misuse / non-compliance allegations] | L | H | [Third-party audit; public dashboard; documentation] |

## 14.2  Crisis & Escalation Protocol

- Operational issues: escalated by Programme Manager to District Coordinator within 48 hours.

- Financial / procurement issues: escalated to DMFT Cell / Member Secretary within 7 days.

- Safety or compliance incidents: immediately escalated to Collector with written incident report.

# SECTION 15 — Institutional Convergence & Department Mapping

📌 GUIDANCE — Institutional Convergence & Department Mapping • MP-led DMFT proposals work best when they show convergence with existing govt schemes & departments. • Name the specific government departments, their role, and the formal mechanism of coordination. • Add a short note on existing MoU / coordination history if any.

## 15.1  Convergence Architecture

«1 paragraph describing how this project sits at the intersection of DMFT funding + line department delivery + NGO implementation support.»

## 15.2  Department-Wise Convergence Matrix

| Department | Role in this Project | Convergence Mechanism |
| --- | --- | --- |
| District Administration | [oversight & coordination] | DMFT Council & monthly review |
| DMFT Cell | [funding & compliance] | Tranche releases & quarterly reports |
| Education Dept / Samagra Shiksha | [if applicable] | [mechanism] |
| Health Dept / NHM | [if applicable] | [mechanism] |
| Women & Child Welfare | [if applicable] | [mechanism] |
| Tribal Welfare | [if applicable] | [mechanism] |
| Panchayat Raj & Rural Development | [if applicable] | [mechanism] |
| Skill Development / TASK / TGSDS | [if applicable] | [mechanism] |
| Telangana State Pollution Control Board / Mining | [if applicable] | [mechanism] |

## 15.3  Stakeholder Coordination Forums

- District-Level Project Steering Committee — chaired by Collector; quarterly.

- Mandal-Level Coordination Meeting — chaired by MRO; monthly.

- Institutional Focal-Person Meeting — convened by Implementation Partner; monthly.

## 15.4  Existing Institutional Linkages of Give For Society

«List existing MoUs, collaborations, government recognitions (e.g. Telangana Governor's Excellence Award 2025), and prior implementation history that supports credibility of the partnership.»

# SECTION 16 — About Give For Society

## 16.1  Organisational Profile

«2–3 paragraphs: registration details, year established, vision, focus areas, geographic spread, and current scale.»

## 16.2  Focus Areas

- Menstrual Hygiene & Adolescent Dignity Initiatives

- School Infrastructure & Educational Modernization

- Integrated Learning Centers (ILCs) & Community Resource Centres

- Health, WASH & Sanitation Programmes

- Youth Skilling, Digital Literacy & Employability

- Women Empowerment & SHG Strengthening

## 16.3  Recognition & Credibility

- Telangana Governor's Excellence Award 2025 — for contributions in menstrual hygiene, educational support, community development, and social impact.

- [Other awards / recognitions — list]

- [Institutional MoUs — list]

## 16.4  Implementation Track Record

«Brief summary of past project portfolio — number of beneficiaries reached, geographies covered, types of interventions delivered.»

## 16.5  Role in This Project

- Technical & implementation coordination.

- Institutional engagement and on-ground delivery.

- Beneficiary mobilization & community engagement.

- Capacity building, training & content development.

- M&E, documentation, and reporting to DMFT.

- Convergence facilitation with line departments.

# SECTION 17 — Annexures

📌 GUIDANCE — Annexures • Annexures provide evidence backing the proposal. They are referenced in the body but kept at the back. • Common required annexures listed below — add or remove based on project specifics.

| Annexure # | Description | Status |
| --- | --- | --- |
| Annexure 1 | NGO Registration Documents (Trust Deed / 12A / 80G / FCRA) | [Pending / Attached] |
| Annexure 2 | Telangana Governor's Excellence Award Documentation | [status] |
| Annexure 3 | Institutional Collaboration / MoU Documents | [status] |
| Annexure 4 | PMKKKY / DMFT Alignment References | [status] |
| Annexure 5 | District Institutional Coverage List | [status] |
| Annexure 6 | Baseline Assessment Format & Sample Data | [status] |
| Annexure 7 | Technical Specifications of Key Infrastructure / Equipment | [status] |
| Annexure 8 | Sample Awareness Materials & IEC Concepts | [status] |
| Annexure 9 | Photographs of Pilot Activities & Institutional Engagement | [status] |
| Annexure 10 | Proposed District-Level Implementation Framework Diagram | [status] |
| Annexure 11 | Vendor Quotations / Cost-Comparison Reference Sheet | [status] |
| Annexure 12 | Sample MoU Format with Implementation Partner | [status] |

# Annexure 0 — Section Status Tracker

To be maintained at the front of each project DPR. Status options: Not Started / Drafted / Reviewed / Finalized.

| # | Section | Status | Owner | Last Updated |
| --- | --- | --- | --- | --- |
| 1 | Executive Summary | [status] | [name] | [date] |
| 2 | District Context | [status] | [name] | [date] |
| 3 | Problem Statement | [status] | [name] | [date] |
| 4 | PMKKKY / DMFT Alignment | [status] | [name] | [date] |
| 5 | Project Objectives | [status] | [name] | [date] |
| 6 | Target Beneficiaries | [status] | [name] | [date] |
| 7 | Geographic Coverage | [status] | [name] | [date] |
| 8 | Project Components | [status] | [name] | [date] |
| 9 | Implementation Strategy & Timeline | [status] | [name] | [date] |
| 10 | Detailed Budget & Cost Justification | [status] | [name] | [date] |
| 11 | Procurement & Operational Model | [status] | [name] | [date] |
| 12 | Monitoring Framework & KPI Matrix | [status] | [name] | [date] |
| 13 | Sustainability Plan | [status] | [name] | [date] |
| 14 | Risk Assessment & Mitigation | [status] | [name] | [date] |
| 15 | Institutional Convergence & Department Mapping | [status] | [name] | [date] |
| 16 | About Give For Society | [status] | [name] | [date] |
| 17 | Annexures | [status] | [name] | [date] |

END OF STANDARD DPR TEMPLATE

Version 1.0 — Jayashankar Bhupalpally District DMFT Portfolio