## Bank Executive Summary
Give For Society — ₹10 Lakh PANKHUDI Bridge Facility (Medium projects)
Mulugu District, Telangana ¦ Source: PANKHUDI portal API (mulugu.json)
Portfolio Metric | Value
Overall PANKHUDI projects (district) | 50
Unique Anganwadi centres | 99
Reported beneficiaries / impact | 4,529
Overall recorded ceiling | ₹25,00,000
Tier split | 0 Minor · 41 Medium · 9 Complex
Selected for bank financing | 41 Medium projects
Recorded budget of Medium pool | ₹20,50,000
Recommended direct spend (Medium pool) | ₹20,28,000
Facility requested | ₹10,00,000 (revolving pilot; staged)
Complex projects | 9 — excluded pending civil estimate / convergence
Tranche | Class | Projects | Max Drawdown (₹) | Principal Purpose | Release Gate
Tranche 1 | Medium (Wave 1) | 14 | 400000 | Initial vendor / electrical / digital packages | Centre verification + project authorisation
Tranche 2 | Medium (Wave 2) | 27 | 600000 | Remaining medium-scope packages | Tranche 1 completion + reconciliation
Total | Medium | 41 | 1000000 | Reduced, complete, usable Medium scope | Complex projects excluded

## Medium Projects - 41
S.No | Project UID | Project ID | Project Title | Centre(s) | # Centres | Beneficiaries | Recorded (₹) | Most Demanding Items | Recommended Spend (₹) | Bank-Eligible (₹) | Readiness | Phase / Wave
1 | PRJ-2026-0019443 | 19443 | Jangalapally Sector 2 | Incherla - II (36701020120); Jangalapalli - V (36701020114); | 5 | 250 | 50000 | Solar Panel, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 1 – Initial ₹10 lakh
2 | PRJ-2026-0019440 | 19440 | AWC Jangalapally Sector | Kannaigudem (36701020113); Incherla - I (36701020121); Kothu | 20 | 1200 | 50000 | Solar Panel, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 1 – Initial ₹10 lakh
3 | PRJ-2026-0015963 | 15963 | AWC Venkatapur Sector | Veerala thanda (36701020607); OLD LAXMIDEVPETA (Mini) (36701 | 9 | 1005 | 50000 | Cooking Equipments, Tube Lights | 49000 | 49000 | Conditional—scope/data correct | Wave 1 – Initial ₹10 lakh
4 | PRJ-2026-0013573 | 13573 | Egg & Milk Storge Racks | Weavers Colony (36701020401) | 1 | 10 | 50000 | Exhaust Fans, Solar Panel | 49500 | 49500 | Ready after quotations and por | Wave 1 – Initial ₹10 lakh
5 | PRJ-2026-0013542 | 13542 | Egg & Milk Storge Racks | Bank Colony (36701020423); CHINTHAKUNTA (Mini) (36701020422) | 20 | 160 | 50000 | Solar Panel, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 1 – Initial ₹10 lakh
6 | PRJ-2026-0013276 | 13276 | Egg & Milk Storge Racks | Barigalonipalli (36701020123); Incherla - I (36701020121); I | 12 | 150 | 50000 | Cooking Equipments, Tube Lights | 49000 | 49000 | Conditional—scope/data correct | Wave 1 – Initial ₹10 lakh
7 | PRJ-2026-0013112 | 13112 | AWC Laxmidevipeta | Laxmidevpet (36701020619) | 1 | 75 | 50000 | Cooking Equipments, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 1 – Initial ₹10 lakh
8 | PRJ-2026-0013091 | 13091 | AWC Gamponipally | Gamponipally(Mini) (36701020623) | 1 | 14 | 50000 | Cooking Equipments, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 1 – Initial ₹10 lakh
9 | PRJ-2026-0013087 | 13087 | AWC Burugupeta | Burugupeta (36701020624) | 1 | 70 | 50000 | Cooking Equipments, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 1 – Initial ₹10 lakh
10 | PRJ-2026-0013084 | 13084 | AWC Porkapally | Porkapally (36701020611) | 1 | 50 | 50000 | Cooking Equipments, Solar Panel, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 1 – Initial ₹10 lakh
11 | PRJ-2026-0013081 | 13081 | AWC Venkatapur III | Venkatapur - III (36701020604) | 1 | 60 | 50000 | Cooking Equipments, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 1 – Initial ₹10 lakh
12 | PRJ-2026-0013054 | 13054 | AWC Infrastructure | Churchipeta (Mini) (36701040619) | 1 | 21 | 50000 | Smart devices | 40000 | 40000 | Conditional—scope/data correct | Wave 1 – Initial ₹10 lakh
13 | PRJ-2026-0011841 | 11841 | AWC Lambadipally | Lambadpally (36701020620) | 1 | 48 | 50000 | Cooking Equipments, Tube Lights | 49600 | 49600 | Conditional—scope/data correct | Wave 1 – Initial ₹10 lakh
14 | PRJ-2026-0011743 | 11743 | AWC Thimmapur I | Thimmapur-1 (36701020608) | 1 | 26 | 50000 | Cooking Equipments, Tube Lights | 49600 | 49600 | Conditional—scope/data correct | Wave 1 – Initial ₹10 lakh
15 | PRJ-2026-0011460 | 11460 | AWC Venkatapur I | Venkatapur - I (36701020606) | 1 | 110 | 50000 | Cooking Equipments, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
16 | PRJ-2026-0011421 | 11421 | AWC YellareddyPalli | Yellareddypalli (36701020601) | 1 | 50 | 50000 | Cooking Equipments, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
17 | PRJ-2026-0011386 | 11386 | AWC Venkatapur IV | Venkatapur - IV (36701020603) | 1 | 107 | 50000 | Cooking Equipments, Solar Panel, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
18 | PRJ-2026-0011378 | 11378 | Muppanapally-I. | Muppanapally - I (36701010509) | 1 | 16 | 50000 | Tube Lights | 48700 | 48700 | Ready after quotations and por | Wave 2 – Medium project ro
19 | PRJ-2026-0011328 | 11328 | AWC Lingapur | Lingapur (36701020618) | 1 | 35 | 50000 | Cooking Equipments, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
20 | PRJ-2026-0011291 | 11291 | AWC Narsingapur | Narsingapur (36701020614) | 1 | 49 | 50000 | Solar Panel, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
21 | PRJ-2026-0011186 | 11186 | AWC Venkatapur II | Venkatapur - II (36701020605) | 1 | 102 | 50000 | Cooking Equipments, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
22 | PRJ-2026-0011139 | 11139 | AWC Venkatapur II BC Colony | Venkatapur II (Bc col (36701020602) | 1 | 48 | 50000 | Cooking Equipments, Solar Panel, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
23 | PRJ-2026-0010963 | 10963 | AWC Andugulamani | Andugulamani (36701020625) | 1 | 51 | 50000 | Cooking Equipments, Solar Panel, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
24 | PRJ-2026-0010774 | 10774 | AWC Chinnagunturupalli 2 | Chinnagunturpalli -2 (36701020217) | 1 | 27 | 50000 | Cooking Equipments, Tube Lights | 49600 | 49600 | Conditional—scope/data correct | Wave 2 – Medium project ro
25 | PRJ-2026-0010716 | 10716 | AWC Ramihnagarthanda | RAHIMNAGARTHANDA (Mini) (36701020208) | 1 | 24 | 50000 | Cooking Equipments, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
26 | PRJ-2026-0010671 | 10671 | AWC | Shivathanda (36701020204) | 1 | 20 | 50000 | Cooking Equipments, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
27 | PRJ-2026-0010633 | 10633 | AWC Sreeramulapalli | Sreeramulapalli (36687040422) | 1 | 84 | 50000 | Cooking Equipments, Projectors, Solar Panel, | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
28 | PRJ-2026-0010589 | 10589 | AWC Pandikunta I | Pandikunta - I (36701020211) | 1 | 59 | 50000 | Cooking Equipments, Solar Panel, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
29 | PRJ-2026-0010539 | 10539 | AWC Annampalli | ANNAMPALLI (36701020222) | 1 | 30 | 50000 | Cooking Equipments, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
30 | PRJ-2026-0010430 | 10430 | AWC Ramsing Thanda | RAMSING THANDA (Mini) (36701020207) | 1 | 18 | 50000 | Cooking Equipments, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
31 | PRJ-2026-0010329 | 10329 | AWC Gurthuruthanda | Gurthuruthanda (36701020216) | 1 | 42 | 50000 | Solar Panel, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
32 | PRJ-2026-0010287 | 10287 | AWC Jaggannapet | Jaggannapet (36701020215) | 1 | 41 | 50000 | Cooking Equipments, Solar Panel, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
33 | PRJ-2026-0010211 | 10211 | AWC Chinnagunturpalli -1 | Chinnagunturpalli -1 (36701020218) | 1 | 12 | 50000 | Cooking Equipments, Solar Panel, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
34 | PRJ-2026-0009008 | 9008 | AWC Pandikunta - II | Pandikunta - II (36701020210) | 1 | 53 | 50000 | Cooking Equipments, Solar Panel, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
35 | PRJ-2026-0008796 | 8796 | AWC Kodeshalakunta | Kodeshalakunta (36701020214) | 1 | 11 | 50000 | Cooking Equipments, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
36 | PRJ-2026-0008670 | 8670 | AWC Mansingh thanda | Mansingh thanda (36701020213) | 1 | 47 | 50000 | Cooking Equipments, Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
37 | PRJ-2026-0008392 | 8392 | AWC Sarangapalli | Sarangapalli (36701020205) | 1 | 20 | 50000 | Cooking Equipments, Solar Panel, Tube Lights | 44600 | 44600 | Conditional—scope/data correct | Wave 2 – Medium project ro
38 | PRJ-2026-0008135 | 8135 | AWC VENKATESHWARLAPALLI | VENKATESHWARLAPALLI (Mini) (36701020201) | 1 | 15 | 50000 | Tube Lights | 50000 | 50000 | Conditional—scope/data correct | Wave 2 – Medium project ro
39 | PRJ-2026-0007936 | 7936 | AWC ABBAPUR | Abbapur (36701020223) | 1 | 55 | 50000 | Cooking Equipments, Solar Panel, Tube Lights | 49000 | 49000 | Conditional—scope/data correct | Wave 2 – Medium project ro
40 | PRJ-2026-0007797 | 7797 | AWC Infrastructure | Puligundam (36701020209) | 1 | 15 | 50000 | Tube Lights | 49400 | 49400 | Conditional—scope/data correct | Wave 2 – Medium project ro
41 | PRJ-2026-0007735 | 7735 | AWC Infrastructure | Chandhruthanda (36701020219) | 1 | 30 | 50000 | Cooking Equipments, Smart devices, Solar Pan | 50000 | 50000 | Ready after quotations and por | Wave 2 – Medium project ro

## Methodology & Selection
Selection basis
- District: Mulugu (50 live PANKHUDI projects; 0 Minor, 41 Medium, 9 Complex).
- This dataset has no Minor projects; the bridge therefore targets the Medium tier only.
- Medium = Electrical Infrastructure and Digital Infrastructure line items (solar, tube lights, cooking equipment, Wi-Fi).
- Complex (Civil Infrastructure) projects are excluded pending civil estimates / convergence.
Financial basis
- Recorded budget of the 41-project Medium pool: ₹20,50,000 (₹50,000 x 41).
- Recommended direct spend for the reduced, usable scope: ₹20,28,000.
- Facility requested: ₹10,00,000 as an initial revolving pilot — not financing of the entire Medium pool.
- Staged: Tranche 1 (Wave 1, up to ₹4L) then Tranche 2 (Wave 2, up to ₹6L).
- Per-project drawdown finalised against quotations / GeM / State SoR before release.
- Repayment from project completion-linked releases / CSR / government convergence against submitted evidence.